Code
of practice

Information technologies
e-Learning

Guidelines

The Code of practice has been translated in English by S2NET, a Leonardo da Vinci programme
Foreword
This Code of practice is presented, written and devised on the initiative of AFNOR, and represents the consensus obtained within the group of participants identified in this document. / Its use is voluntary. / This code of practice has not been subjected to the approval procedure and may not under any circumstances be considered equivalent to a French standard.
Copyright ©
The present document is protected by the provisions of Book 1 of the Intellectual Property Code concerning artistic and literary property. Reproduction of whatever kind is an infringement of copyright and represents an offence.
Translation of 2nd edition May 2004

AFNOR
http://www.afnor.fr
BP Z 76-001	 AFNOR	April 2004

Links with existing documents
At the issue date of the present document there are no European or international works dealing with the same subject.

Note
This document has been written by French experts, and was intended primarily to be used in France only. The growing interest in best practices in e-learning at European and international level lead the French Forum for Open and Distance learning (FFFOD) to have this document translated into English, in order to facilitate its dissemination among expert groups or stakeholders interested in e-learning quality assurance or in e-learning standardisation processes.
Though it is now available in English, foreigners shall nonetheless keep in mind that many considerations in this document are based on and take into account specific aspects of the French educational and vocational training context, that recommendations have been devised for implementing e-learning in this particular context, and that some of these recommendations might not apply without adaptation to any other national educational or vocational training environment.

Drafting committee

Project manager
Jacques Naymark, Savoirs Interactifs /FFFOD

Experts
Anne-Claire Cohen, FFFOD
Françoise Desmaison, Cned
Pierre Eckert, AFPA CNEFAD
Françoise GERARD, Centre Inffo
Frédéric HAEUW, ALGORA
Anne-Marie HUSSON, Préau-CCIP

With the participation of
Sylvie Arbouy, AFNOR Standardization
and Olivier AUDEBERT, AFNOR Certification

Acknowledgements

Organizations having contributed towards the drawing up of the code of practice: AFPA, ALGORA, Centre Inffo, CNED, Le Preau CCIP, Savoirs Interactifs
Organizations having contributed financially towards the drawing up of the code of practice: AFPA, CESI, CNED, DGEFP, Ministry of Education and Research.

Contributors to the validation or enrichment of the Code of practice

ADDEO, Jacques PEYRONDET
ADEFOR, Marie-Françoise CHAPELLE
AFPA, Dominique Anne BARON
AFPA, Dominique SAINT-ARAILLE
AFPA, Jean GUILVOUT
AFPA, Mireille FERRE
AFPA, Raymond CSZTERNASTY
AGEFOS PME, Pascale TERRASSON
ALGORA, Arnaud COULON
ALGORA, Claude LEPINEUX
ALGORA, Philippe MORIN
ANFA, Jean-Pierre HERVELEU
ANFA, Julien GOSSET
APP Réseau national, Odile DEBLIQUI
AUDRECO, Michel GEORGEL
BANQUE DE FRANCE, Elisabeth MORANGE
BEODL, Willy VANDAMME
BNP PARIBAS, Monique Benaily
BNP-PARIBAS, Monique BENAILY
CARREFOUR NUMERIQUE — Cité des Sciences, Pascaline BLANDIN
CCIP, Jeanne SCHNEIDER
CEGOS, Claire BEYOU
CEGOS, Jacques FAYET
CESI, Bernard BLANDIN
CFTC, Jacques ARNAUD
CHANED / REVUE D'ETUDES, Jean PIONNIER
CNAM, Pierre CASPAR
CNEAP, Alain GACHIGNARD
CNED, Chantal RIBOREAU
CNED, Florence QUILLIOT
CNED, Françoise LECLERCQ
CNED, Jean-Louis DECHERAT
CNPR, Bruno LEBATTEUX
CRI, Anne DUIKER
CSFC Ile de France, Annette GARCIA
CTN, Francine ROCHEFORT
DEMOS SA, Gilles MACCHIA
DRTEFP Ile de France, Dominique CROISIER
E.MEDIA FORMATION, Noëlle BAILLON-BACHOC
E.MISSION, Jean-Pierre MICHEL
E.MISSION, Patrick CHEVALIER
EDEN, Ildiko MAZAR
EDF GDF, Anne-Marie VEYRUNES
EFODL, Bert COOLEN
EFODL, Helga VAN HEYSBROECK
EFODL, Johan VAN OOST
EUROPACE, Annemie BOONEN
FFP / CESI, Jacques BAHRY
FONGECIF Ile de France, Myriam PUYRAVAU
FOREM FORMATION, Pierre MICHEL
FRANCE TELECOM FORMATION, Alain ASTOURIC
FRANCE TELECOM FORMATION, Christine RABIS
IDS, Christine BATIME
IFG, Christophe BOISSEAU
IFG, Nathalie BALOCHE
IFTH, Laurence LE CARRE
INFFOLOR, Christelle DROUOT
INFFOLOR, Emmanuel JOURNOT
INTERFOR-SIA, Hassan LAARAJ
ISF, Marc MANGUIN
ISI, Olivier LAMIRAULT
KLR, Anne BOUTHRY
KLR, Christophe JOURDAIN
KTM SYSTEM, Robert BECKER
LEARNPERFECT, Stéphane MOLINARO
MAIF, Sylvie PELLETIER
Ministry of Education, Annie LE GOURIÉRES
Ministry of Education, Patrice CLODORE
Ministry of Employment and Solidarity — DGEFP, Nadine KEBE
NADE, Torhild SLAATTO
OPQF, Hervé BARBOTIN
ORACLE, Jean-Jacques BOUET
PREAU — CCI de Paris, Gilles FREYSSINET
PSA Peugeot Citroën, Laurence DELORD
PSA, Laurence Delord
Regional Council of Aquitaine, Hélène KHOURI
RENAULT, Anne BRONNEC
RENAULT, Catherine SAILLY
SAVOIRS POUR TOUS, Bruno FAJNZILBERG
SCHNEIDER , Marc Tirel
SCHNEIDER , Martin Roulleaux-Dugage
SEB Tilburg, Joël DE BRUIJN
SEB Tilburg, Peter ZACHT
SEB Tilburg, Winne DE WERD
SNEPAT-FO, Yves LAINE
SUEZ  bricheuxpalier@suez.com
SVDT, Coen FREE
SVDT, Josée BOURS
SVDT, Ton VAN DER MOOLEN
SVDT, Yvonne MOERMAN
TELELANGUE, Laurent Hayat
University of Nancy, Véronique DUVEAU-PATUREAU
University of Paris IX Dauphine — DEP, Evelyne DERET
University of PARIS VIII, Geneviève JACQUINOT
University of Paris X — Nanterre, Claire GARCIN
University of Paris X — Nanterre, Olivia ROUX
University P&M Curie - Paris VI - FP, Delphine RICORDEL
University P&M Curie - Paris VI – FP, Jean UEBERSFELD
WIDIL Industries, Hubert BONAL

Contents
        Page

# Introduction
This Code of Practice (COP) in e-learning is the fruit of the mobilization of a profession – grouped together within the French Forum for Open and Distance Learning – FFFOD (Forum Français pour la Formation Ouverte et à Distance) – concerned about the quality of its services with regard to development.
This approach is the result of a desire for convergence between French practices and international standardization work within the framework of the ISO. It was believed necessary to take part in this work, firstly to find out about and understand the implications of globalization, and secondly in order to contribute to a realistic analysis and thus take part in the emergence of international standards which take into account our economy and our cultural and social context. This approach is also the result of a desire for consistency in the face of a worrying discrepancy between marketing arguments – “reduce your training budget by 60% with e-learning” – and actual practice in using information and communication technologies (ICT) in the field of training taken in all its diversity. To return to the reason, within a competitive context it was necessary for professionals to accept to share and mutualize practice, to separate the wheat from the chaff and thus build up the collective intelligence that the emergence of the information society and the knowledge economy require.
In more concrete terms, this code of practice has been constructed using an empirical and pragmatic approach based on a rigorous and demanding process of clarifying practice and use. After initially collecting information in the form of interviews, the rules, premises and conditions for implementation have been brought out, in a necessarily conceptual form. It was necessary to deconceptualize the experiences from the interviews carried out and the documentary analyses, to extract transferable elements which can be generalized that could be the subject of a series of recommendations, and to organize them as a process.
The question arose of how the incorporation of ICT in the field of training should be taken into account in normative reflection. The purpose of the study undertaken in this way by e-learning professionals – with regard to the standardization work already carried out in the field of training – is to determine the specificities and invariants, in terms of procedures, of systems incorporating ICT compared to traditional training.
The simplest, but also the most simplistic solution would have been to apply the existing standards for training (c.f. NF X 50) to e-learning. But the method of identifying good practice by analysing concrete examples has been deemed to be more dynamic, rewarding and revealing than a rather doubtful application of training standards. The document written in this way should therefore make it possible to complete the normative tools that exist for traditional training methods; it does not contradict the work carried out previously by training professionals, but must provide a structuring framework for creating a quality service.

## Who is the code of practice intended for?
This code of practice is intended for those involved in training: on the one hand the professionals who are the decision-makers, project managers, trainers, designers and tutors and on the other hand the prescribers and financiers of the training course. In its present form it is not intended as a document that is directly aimed at learners.

## Area of application of the code of practice
Traditional definitions and boundaries for training are partly challenged by the widespread use of ICT in training practice. For example: the criterion for eligibility of training expenses does not allow general investments in the information system to be taken into account. The formal or informal nature of exchanges between learners and information retrieval on the Web are other examples of criteria that are not taken into account in traditional accounts of training activities.
The area of application of the code of practice lies within the scope of continuing vocational training. It concerns training systems that are aimed at developing professional skills and that use microcomputers and/or the Internet in the training activities. It should be noted that we have favoured the inclusion of e-learning within a training system, while excluding from the area of application the purchase of off-the-shelf self-training software programs from a supermarket or isolated and one-off offers on the Web.

## A “customer-based” approach
The general approach of this COP is based on the “customer” of e-learning. Within the French context of the third-party payer this means a “plural” customer: the prescriber, the financier and the learner.
The learner is at the heart of the COP regardless of the diversity of the different contexts. The following table shows the main advantages and disadvantages of E-learning from the learner’s point of view:

Advantages	Disadvantages
The reduction or absence of travelling (time-saving, reduction in travel expenses)	Possible solitude and lack of stimulation / The risk of transfer of cost to the learner
The personalized pace of work that facilitates time management and distribution (free time, training, work)	The difficulty for some learners in working alone. Ability to organize their time
Personalization and autonomy in learning / Not the sole monitoring and judgement of the trainer, but shared management of assessment	The difficulty of autonomous learning / Difficulties mastering a method of work
The possibility of learning while making mistakes	The difficulty of constructing one’s own approach to learning

## A process approach
According to the standardized definition, a process is: “A collection of correlated or interactive activities that transform input elements into output elements” (ISO 9000:2000 standard). It is therefore a sequence of activities carried out with the help of resources (employees, equipment, teaching materials, information) of which the final result expected is a product or a service.
A process presupposes:
- measurable input elements (and in particular the preconditions to the implementation of an initiative);
- added value;
- measurable output elements, in accordance with acceptance criteria;
- reproducible nature.
We have therefore selected this approach in drawing up the code of practice.
## An upgradeable document
Although it is almost fully developed for some of these processes, e-learning is not yet fully stabilized. Indeed, on the one hand the relationship between pedagogical methods and technology remains asynchronous: educational practices develop slowly whereas technology remains extremely dynamic and on the other hand questions relating to the assessment of e-learning have proved to be difficult to clarify and formalize and it would be presumptuous to claim to have a final solution to this question!
This reference document must therefore be developed at a rate that is still to be defined. Discernible developments must also be taken into account such as:
- the convergence of e-learning as a skills and knowledge management tool (cf. convergence of e-learning and knowledge management: http://www.fffod.org/fr/frame_univ.asp);
- the emergence of collaborative working and learning practices that are in full expansion.
In addition, the specificity of code of practice, which are not a forward-looking document by the very nature of their approach (clarifying on the basis of formalization of shared experience), strengthens the need to revise this corpus of experiences regularly in order to ensure the continuity of the collective analysis.
# Analysis stage
## Specificity of the process
e-learning is in the process of being developed and of coming into general use in all training activities in very varied forms. The innovatory nature of these practices is therefore part of a process of change in relation to usual practices on several points: economic logic of investment, total or partial break-up of training times and areas etc.
These potential changes involve adding an additional dimension to the strategic analysis that precedes all "traditional" training solutions, if they involve substantial investments. Indeed, in order to provide more effective control, it is important to weigh up on the one hand the advantages and progress, and on the other hand the risks inherent in the introduction of new methods of training and technologies that are mastered in varying degrees.
### Diversity of contexts
To achieve the right balance between supply and demand, it is first necessary to distinguish the logic and the socioeconomic and cultural environment of the e-learning project. The following elements may be at the origin of the request:
- search for an improvement in the cost/results ratio for more effective training;
- training requirements potentially on the increase;
- search for improved adaptation of the education / training systems to necessary developments in skills of the economic world;
- use of increasingly widespread possibilities for access to knowledge that are simple, broader and open to meet the rapid development of certain lines of business;
- taking into account the issue of specific types of learner (elderly, isolated or disabled employees etc.);
- political and social necessity of guaranteeing access to knowledge and training for all;
- importance given to territories as regards vocational training.
### Analysis of advantages and risks
As in all projects that involve considerable human and financial investments it is essential to take the risk into account and this is particularly the case for e-learning.
1)	Identify and reconcile the objectives of the offerer, prescriber, financier and learner, and begin the joint construction of the project.
2)	Assess the impact of changes caused by the project.
3)	Compensate for the fact that the recovery of the different experiences is not immediate (guarantee the elements that make it possible to foresee, to plan and to anticipate).
### Added value of e-learning
This involves identifying the expected added value of e-learning in comparison with a traditional course. Is the purpose to provide access to training without the constraints of time or place, to reach a new target population, to reform or revitalize a training course, to deal with difficulties of availability or mobility of learners, to innovate (marketing approach), to offer additional services to face-to-face instruction, to develop exchanges and communication between all those involved in training, to tailor the training to individual needs, to reduce training costs, to offer the same quality of training to a maximum number of beneficiaries, to enable rapid and flexible access to training, to favour continuous inputs / outputs?
Before formulating a response to a request for training, this stage therefore involves examining two subprocesses:
- strategic analysis that clarifies the context of the request (environment, issues, the objectives of the different parties);
- feasibility of the request (analysis of the requirements and resources available for implementing the programme).
## Strategic analysis
The strategic analysis stage is essential: it involves developing a commitment to implement e-learning in a way that is meaningful and lasting. It is then necessary to formalize the opportunities and constraints in order to simplify the decision-making process. Analysing the preconditions does not involve providing final solutions or choices: it involves clarifying and delimiting the scope of the project, its context and the existing basis for its implementation. This analysis provides the elements required to compare, choose and decide on the characteristics of the final project.
Sometimes the strategic analysis is already complete and it is simply necessary to study it. But even if it is urgent, a minimum amount of time for reflection must be devoted to this strategic analysis.
### Clarify the issues for the different parties
Strategic analysis makes it possible to clarify and formalize the issues, objectives and expected results.
4)	Clarify the requirements and aims of the project.
5)	Clarify the aims expected by the prescriber, the financier and the learners.
6)	Define the place of the project in the development strategy.
7)	Identify the assets and resources available for the project (political, financial, technological, organizational and sociocultural).
8)	Locate possible restraints (political, financial, technological, organizational and sociocultural).
9)	Identify the political and organizational constraints and key requirements: training at the work station, training within a very short time limit etc.
10)	Incorporate the constraints linked to the aim of the training course (leading to a qualification, certification etc.) and the consequences in terms of validation.
11)	Take into account the constraints in terms of time limits for the completion of the project.
### Specify the added value
E-learning may be chosen as a productivity tool (better training, more employees, within shorter time limits with the same budget) and/or as a tool for competitiveness (strong and/or urgent training requirements).
12)	Identify and formalize the precise elements of the environment that constitute the context justifying the appropriateness of investing in the development of e-learning (this involves indicating the political, economic, sociological and professional elements to which the organization refers to develop e-learning).
13)	Specify the elements of the internal and/or external context of the organization that have led or will lead to the commitment to develop e-learning.
14)	Position the e-learning from a strategic point of view among the other strategic orientations of the organization (Experiential Learning Assessment, etc.).
15)	Provide an overall analysis of the opportunities and requirements of the market as regards e-learning solutions.
16)	Identify market segments, professional sectors and target populations for which e-learning opportunities are meaningful.
### Provide competitive intelligence
The e-learning market is overloaded by the number and variety of offers. To propose a new offer you must have a thorough knowledge of what already exists:
- either to assess the factors for commercial success by good positioning;
- or to compare and benefit from the experiences and assets of what already exists.
In principle the possibilities offered by ICT enable organizations regardless of their country of origin to intervene in all training markets.
17)	Examine the constraints of this environment and the possible development of its own advantages.
18)	Find and analyse the existing or potential competition.
19)	Identify the strengths and weaknesses of the organization compared to the competition:
- tangible investments;
- intangible investments;
- capacity for innovation;
- skills available;
- flexibility of the organizations.
20)	Examine the offers that already exist within the market (private, State, commercial or non commercial), in order to find out information concerning:
- market shares;
- target population;
- communications and methods of promotion of the offer;
- services proposed.
### Envisage possible partnerships
In the face of the complexity of the area of application of e-learning, the different professions that it appeals to, its ongoing development and its economic aspects, partnerships and/or subcontracting are among the strategic choices possible in order to:
- share the risks;
- remain focussed on one's line of business and expertise;
- create synergies by relying on external skills;
- increase collective understanding;
- join a network.
21)	Identify the areas of skills necessary for the project by making the choice to “stay within your line of business” while at the same time resorting to external skills for those that are weaker or unavailable within the organization. This outsourcing may take the form of a partnership or simple subcontracting, as the case may be.
## Feasibility study
After strategic analysis, this second subprocess has a variable area of application depending on the scope of the envisaged system. The position of certain items may vary depending on the size of the operator. Some will see this as part of the strategy and others as already part of the construction of the system.
In certain cases the feasibility study may directly concern a real and current e-learning solution without systematically going through the strategic analysis stage, certain aspects of which it necessarily covers.
This feasibility study requires sufficient time to apprehend, implement and structure the basic elements of the project. These elements constitute the specific framework of the system that will be taken into account in all of the processes, and possibly be used to decide on the methods and ultimately take the necessary decisions.
### Specify the goals of the training course
22)	Identify the specific elements on which the request to formulate an e-learning solution is based (e.g.: requirements of the sponsors, of the target populations).
23)	Describe the detailed effects anticipated and the advantages of an e-learning type solution.
24)	Specify whether the training objectives are aimed at general knowledge or professional skills referenced in the work system, in order to decide what it is possible and pertinent to deal with entirely through distance learning or rather through using mixed methods.
25)	State whether the training course makes it possible to obtain a diploma or certification. This then requires the configuration and organization of principles of assessment and validation of e-learning.
### Identify the training requirements
This involves estimating the number of people to be trained, identifying their training requirements, their expectations and their motivation.
26)	Assess the implicit and explicit training requirements.
27)	Estimate the number of potential learners (short, medium and long term).
28)	Estimate the buying intentions for an offer on the market, identify the price range (for an in-house training offer, estimate the number of people to train, for what length of time).
29)	Specify the objectives of the training course for the future learners (their training project) and the resulting expectations.
30)	Estimate their level of motivation for an e-learning project.
31)	Specify the desired or favoured training methods.
32)	Identify the main elements affected by the characteristics of the target population.
### Organize the project
In order to construct, draw up, lead and assess e-learning, resources are required (human, technological, financial, legal, commercial, communications, administrative, maintenance and updating, coordination etc.). It is therefore necessary to carry out a detailed analysis of the material and human context in order to locate, in relation to the e-learning project and its aims:
- the existing resources and the methods of incorporating them in the project that can be directly mobilized or that must be modified in order to be used,
- the resources that are lacking or deficient and suggest solutions.
33)	Organize the management and implementation of the project (plan the stages and systems of negotiation and regulation between the parties).
34)	Specify the skills required for constructing and implementing e-learning, in particular the role of the trainers.
35)	Plan the organization of the assessment of the system:
- withdrawal from the course;
- satisfaction of customers / learners in particular in relation to the specific characteristics of e-learning;
- measurement of the impact in relation to the objectives of the training course.
#### Analyse the existing context
This involves analysing the resources available or to be sought for each aspect.
36)	List the human resources.
37)	Specify the skills required for constructing and implementing e-learning, in particular the role of the trainers.
38)	Integrate the organizational aspects (the infrastructure and in particular the IT resources, workload and planning of the project in terms of time limits and due dates).
39)	Take into account the internal understanding of training in general and e-learning in particular (e.g.: locate possible sociocultural reservations) and consider the financial resources available, the commercial arguments / communications and educational resources.
#### Build up partnerships
Organizing e-learning requires many skills: technological skills, pedagogical skills, and those linked to mediatization of the content. If it is sometimes tempting to want to do everything alone, it is preferable in e-learning to identify the areas of skills and to “remain within one’s line of business”: the trainer is not necessarily the best person to deal with the mediatization of the content. Conversely a computer graphics designer does not necessarily have pedagogical skills. In addition, depending on the contexts and the requests, it may be advantageous to mutualize the design of the training resources on the basis of additional areas of competence in terms of disciplinary or vocational content.
40)	Identify the skills necessary for the project.
41)	Lay down the administrative and legal rules of the partnership and/or subcontracting, particularly concerning the creation of resources (in terms of intellectual property).
42)	Specify who does what, within what time limits and with what methods.
In mixed or hybrid training it is necessary to combine two types of skills: a general ability linked to knowledge (specific teaching knowledge, distribution of content, educational follow-up, validation etc.) and an ability linked to local support (support for motivation, technical support for access to technologies etc.).
This type of system requires a partnership based on this network of skills.
43)	Plan the methods of exchanges and reporting between the organizations and the different parties involved.
44)	Plan the formalization by contract with learners of the methods of intervention and of contacting the different types of contributors.
For geographical cover
e-learning should make it possible to meet the needs of the target population. Within a geographical zone (an area, an employment area, a region or even at the national and international level), mutualization of services is possible in an exchange process. For example, a network of Apprentice Training Centres (Centre de Formation d’Apprentis – CFA) and Learning Centres (Ateliers de Pédagogie Personnalisée – APP) may contribute to the introduction of “sharing of rare resources” for infrequent fields or requests, by making resources and content experts available to other centres.
45)	Identify the areas of expertise.
46)	Take competitive aspects into account.
47)	Determine the rules for exchange.
For professionalization of the parties
Professionalization of the parties involved in e-learning, on a geographical basis which can be regional, national or international, is another field in which partnerships are advantageous and lead to the development of a varied and coherent offer.
48)	Share expertise (people, internal resources).
49)	Work out the financial engineering.
50)	Organize the professionalization system.
51)	Plan the conditions of transfers in each of the organizations.
#### Education and technology watch
52)	Compare the pedagogical models implemented, the innovations provided by ICT (simulations, exercisers etc.) in terms of value added for an identical or similar training offer.
53)	Compare functionalities, prices, advantages and disadvantages (in particular adaptability and capacity for development), for existing tools on the market.
### Analyse costs and calculate the breakeven threshold
The feasibility of the project is based on an analysis of the structure of fixed and variable costs and the conditions for short and medium term profitability.
54)	Estimate the projected costs of the different types of investment: market analysis, technological and organizational investment, training resources, logistics, experimentation, internal and external communications, marketing approach, assessment and improvement.
55)	Calculate the breakeven threshold of the system (break-even point according to the economic logic accepted).
56)	Estimate the production costs and sales prices of the training course.
57)	Possibly find co-financing (public, partnership, European etc.).

### Draw up the decision support file
#### The final decision support file consists in giving managers the elements needed to decide what to do and what not to do.
58)	Synthesize the positive and negative aspects of the project, risk factors and elements of comparison between an e-learning solution and a traditional solution.
This analysis can be based on the following three aspects:
- the training project (target population, training objectives, educational benefits specific to the implementation of the training technologies) and its positioning in terms of marketing;
- technical constraints (permanence, maintenance and development, skills mobilized);
- economic and financial constraints.

# Construction stage
## Specificity of the process
After the stage of preliminary analysis which was of use in shaping the project and in specifying its strategic positioning, it is necessary to build the training system in all its aspects (pedagogical and technological aspects, human resources, methods of learning support, organization etc.). We will single out two main areas where the usual distinction is found between training course engineering and pedagogical engineering:
- overall design of the learning system;
- design of educational resources.
These two area are part of a project approach, in a context of service (e.g.: response by a specific offer to a particular request) and their purpose is to be implemented and distributed to the different customers, both learners and the prescriber and financier.

We have distinguished this process of training course and pedagogical engineering from the process described in the following chapter “Equipment stage”. In the opinion of training professionals, the anteriority of the design process in relation to the drawing up process indicates that the technological aspect of e-learning is used, as its name indicates, to draw up a training system. However the reality of e-learning is more complex. It involves a subtle dialectic of new opportunities (interactivity, synchronous or asynchronous communications etc.) and of heavy technical constraints (hardware and software, network access etc.). It is this dialectic in particular and its tensions that form the specificity of this code of practice.
The unique aspect of constructing e-learning is that it mobilizes different participants, with different concerns (strategic, educational and economic) and different skills for the same objective (e.g.: response to a request) in order to build a complex system through the multiplicity of the aspects to be managed: pedagogical, financial, legal, political, technological etc.
### A project approach
#### Organization of the project
Only a project approach makes it possible to take into account the involvement of all of the participants in the construction and therefore its progressive appropriation and adaptation to requirements.
The project approach starts with the introduction of a collaborative network:
59)	Form a steering committee (contractor or management of the training institution, representatives of the client, prescriber, financier and partners) which has a political role: it validates and checks that the objectives and requirements of the specifications are indeed respected, that the strategy for action remains coherent.
60)	Form an operational and technical committee, coordinated by a project manager who carries out the various stages of construction according to the skills of each person. Distribution in groups / workshops by subject seems to be the best form of organization (e.g.: content design, technical implementation, communications and training) with regular coordination meetings. For multi-site institutions, each site takes charge of a subject or a task force.
#### An approach by iteration
The project approach includes stages of tests and assessment throughout the construction period, and the necessary adjustments.
61)	Plan tests on the types of presentation (graphics, forms, browsing for the Internet etc.), on the sequences, on the types of media and their practical use, on the types of tools for distribution, for communications, for administration and tests on uses during a pilot project.
62)	Formalize the results of these tests in terms of operational consequences, avoiding ruinous disputes by determining precise criteria and dates.
Besides stage by stage validation of the choices made, tests allow the different parties (managers, contractors, educational designers, tutors, learners and trainers) to be involved in each subprocess of the “construction” stage, and to appropriate the course. Tests are scheduled and provided for during the planning of the project, and far from slowing down the construction process they strengthen it and reinforce the motivation of the teams and their cohesion.
63)	Use these exploratory test stages to favour the appropriation of the course by all of the parties concerned.
In the event that it is the first time the sponsor and training organization(s) have put together an e-learning solution, this iterative approach can be backed up by deliberate implementation of “action-research”. This approach is practised in educational and social innovation processes and leads to:
64)	Using methodological and rigorous support by experts.
65)	Planning the resources for additional training, incorporated in the action of the operators.
66)	Formalizing and “capitalizing” the processes and skills in a knowledge management process.
#### Consultation and communication
The project approach also includes ongoing negotiation and consultation between all of the parties involved (customer, beneficiary, financier, partners, technical, administrative and educational staff) and communication concerning the project, the advance of the work, the difficulties encountered and the solutions found.
67)	Formalize the choices and communicate them in contractual documents (specifications, call for tenders, monitoring and management charts, notes of decisions etc.).
68)	Communicate to facilitate in particular support for changes that the introduction of e-learning involves in certain organizations. This support can be particularly strong for those whose roles/jobs are transformed in e-learning.
## Constructing the training system
This involves constructing the different moments of the training course and their arrangement, specifying the nature and aims of the services offered and of the support. E-learning makes it possible to create a “learning environment”, made up of contents (training programme), acquisition controls, methods of individual and/or collective communication – a whole combination of aspects supported by a more or less sophisticated technological environment.
### Locate the initiative in a typology
E-learning is based “on complementary and plural learning situations in terms of times, places, educational, human and technological mediation and resources”[1]. A system is therefore an intelligent arrangement of varied methods, varying in number as circumstances dictate.
[1] Collectif de Chasseneuil (2001). Accompagner des formations ouvertes. Conférence de consensus. (Supporting open training courses. Consensus conference). L’Harmattan, Paris, p. 177.
At the end of the construction process, the system is all the more adapted to its purpose since the designers have identified the general form that the system will take from the outset. In fact, a good many projects fail through lack of initial clarification of the intentions and model that its designers wish to implement. In the event of the transformation of an existing offer (which is often the case), this engineering of the form also has the advantage of identifying clearly the elements that will be transformed in this way and building reasonable and measured projects that take into account possible resistance to change by the parties involved.
{0>Cette première étape de clarification est nécessaire.<}0{>This initial clarification stage is necessary.<0} {0>On peut pour ce faire se servir par exemple de la typologie utilisée par l’enseignement supérieur {1>fn<1}, qui identifie cinq types de dispositifs à partir de la proportion distance/présence (présentiel enrichi, présentiel amélioré, présentiel réduit, présent restreint, présentiel quasi-inexistant).<}0{>To do this we can for example use the typology used by higher education{1>[2]<1}, which identifies five types of system on the basis of the distance/presence ratio (face-to-face instruction enriched, face-to-face instruction improved, face-to-face instruction reduced, face-to-face instruction limited, face-to-face instruction almost nonexistent). <0}{0>On peut également opter pour la typologie {1>fn<1} construite en croisant le mode de formation (présentiel, à distance, ouvert, ouvert et à distance) et la fonction prioritaire de la technologie (information, communication, information et communication).Réponse à la demande<}0{>We can also use a typology{1>[3]<1} that combines methods of training (face-to-face instruction, distance learning, open learning, e-learning) and the predominant role of technology (information, communication, information and communication).
[2] {0>Direction de la technologie (2001) Compétice, un outil de pilotage des projets TICE par les compétences, Ministère de l’éducation nationale, www.education.fr/competice.<}0{>Direction de la technologie (2001) (Compétice, a tool for management of EICT projects by skills), Ministry of Education, www.education.fr/competice.<0}
[3] {0>B.Blandin (2004), Ingénierie et formations ouvertes et à distance, Traité des sciences et des techniques de formation, 2e édition, Dunod.<}0{>B.Blandin (2004), Ingénierie et formations ouvertes et à distance, Traité des sciences et des techniques de formation (Engineering and open and distance learning courses), 2nd edition, Dunod.<0}

### Response to demand
For e-learning, taking into account the initial demand and requirements expressed or assessed is all the more important since the learner is not in the same time/place/action area as the provider of the system. The effectiveness of the system will be measured by the rates of withdrawal, attendance or educational success, which in turn depend on the appropriateness of the course to the requirements and expectations of the learners. The system is a response to a demand and to formalized and stated training requirements for an identified public and environment.
#### Negotiate
This negotiation clarifies and formalizes the issues and requirements, but in particular it leads to the involvement all of the parties concerned, which results in formalization by contract (e.g.: at this stage, the specifications).
69)	Negotiate with the contractor, the prescriber, the financier and any partners. It is necessary to understand their contexts, requirements (both explicit and implicit) and expectations in order to include these in an offer which not only meets them but also anticipates foreseeable developments.
70)	Enter into dialogue with the learners, the future beneficiaries of the offer. It is necessary:
- to identify and clarify training requirements, the types of skills looked for (knowledge, expertise, life skills) in an individual or collective context, with strong or weak contextualization;
- to find the concrete environment of the training course and the possible or acceptable methods (practices and uses, availability of the beneficiary, computer and multimedia equipment, training places).
#### Specifications of the training course
The specifications describe the anticipated functions of the system and the anticipated computer specifications. Practical experience shows that technological tools must not be chosen at this stage at the risk of favouring a given technology or tools to the detriment of the real training objectives. It is the educational objectives and the compromise between financial, human and organisational constraints that must subsequently determine the criteria for choosing tools.
71)	Include in the specifications:
- the objectives of the training course and the expected results;
- the public(s) concerned and its/their characteristics;
- the resources available and constraints (technical, budgetary etc.);
- the strategic and organisational choices that will determine the general structure of the course: admission-withdrawal ongoing or not, training during working hours or outside working hours, on-site, at home or in the workplace (at the work station or in a dedicated room), principles of monitoring and assessment (assessment criteria), methods of participation of the sponsor/financier in the course (participation in the elaboration of contents, in monitoring, in assessment etc.);
- the medium and long-term developments of the course (flexibility, level of adaptation to new publics, industrialization, transfer to other sites etc.)
#### Know the characteristics of the future learners
It is essential to analyse the profile of those concerned by the e-learning project in order to adapt the training offer (prerequisites, content, learning model, services and adapted resources).
72)	Analyse the sex, age, place of residence and geographic dispersal of the target population.
73)	Analyse the socioprofessional occupation and family status.
74)	Analyse the level of training and period of time since studies were last carried out and the starting levels of general and occupational skills.
75)	Analyse in particular the e-learning experience, level of autonomy, level of facilities, level of familiarization with ICT (this point is decisive in the initial stages).
76)	Identify the elements affected by the characteristics of the target population.
77)	Express the results of the analysis of demand and of the future learners in terms of possible/necessary methods of the system (and possibly compare and negotiate between the requirements and expectations of the sponsor and those of the future learners).
78)	Specify the basic foundations of the pedagogical methods appropriate for the target population as well as the necessary system of technical and learning support.
79)	Formalize the learning structure very precisely (elements of contextualization, learning progression, formalization of learning content as such, elaboration of training exercises) and the various methods of assessment.
80)	Define the organization of the training course, the technical resources required and the probable places and times for learning so that the course goes as smoothly as possible.
### Define the training methods
#### Contextualize e-learning engineering
This involves tracing the expectations, practices and uses on the basis of a rigorous analysis of requirements. On the one hand it involves determining the main educational strategies corresponding to the three main areas of success of learners (motivation, autonomy, socialization) for the targeted population and context, and on the other hand controlling innovation so that it is rewarding and accepted by all of the parties: each person should be in an all-win situation.
81)	Analyse the different levels of distance to be taken into account (geographical, temporal, cognitive, social, technical and psychological); identify the predisposing factors, the pitfalls to be avoided, and compare them with the levels of autonomy, of motivation and the context of the learners.
82)	Carry out a technological study beforehand to choose the most appropriate solutions.
83)	Define these methods by simulating the daily working conditions of the structure, regardless of the conditions of introduction of the project, in particular if the project is introduced using exceptional means which cannot be reproduced in the deployment stage.
Structure the organization of e-learning according to the criteria selected:
84)	Possibly specify the face-to-face / distance ratios.
85)	According to the context, plan the implementation of an individual positioning tool.
86)	Describe each stage of the course (cf. following process), specifying for each of them: the corresponding organization, length, content, tools and human resources.
87)	Organize the time areas and geographical areas.
88)	Regulate the distribution between training at home / in the workplace.
89)	Make sure of the appropriateness of the training course to the professional context (educational objective, skills, accessibility, time, technology) so as to avoid two pitfalls: on the one hand the dissociation between the professional context and the training course and on the other hand the subordination of the training course to the professional context (encroachment in terms of time, activities, access and taking responsibility).
90)	Favour the use of a workstation dedicated to training within the context of work.
#### Create conditions for socialization
91)	Define and describe the anticipated requirements for exchange and socialization necessary for e-learning to go smoothly; model the intended exchanges in each of the subsets concerned (nature of the exchanges, objectives, methods and tools); Provide for the tools (forum, chats, email etc.) and organize communications:
- between learners;
- between learners and tutors;
- between learners and professional context;
- between tutors (the whole of the teaching team);
- between tutors and all of the teaching team (platform administrators, network, administrative staff, communications etc.).
92)	Adapt the rituals of standard training (e.g.: general presentation and discussion etc.) to e-learning, and possibly create new ones (e.g.: rituals for distance greeting etc.).
93)	Construct methods of individual and/or collective positioning since, more than in any other system of traditional training, the process of individual positioning on admission to the training course is essential and decisive. It enables real tailoring of the courses to individual needs which is a great advantage of E-learning. It will focus as much on content prerequisites as on prerequisites for autonomy in the use of the pedagogical and technological methods proposed. It also represents the first contact with the system and in some cases enables "tailor-made" individual construction and negotiation of the training course. It can therefore be designed before the other methods of the system. It may also be wise to use identical or similar positioning tools between the preliminary analysis of the target populations, carried out in the feasibility study process, and admission to the training course.
Draw up these methods of positioning, which may be facilitated by digital tools similar to the skills management tools.
#### Define the type of learning support
Support activities are particularly important in e-learning. Defining them with precision is one of the key points of the engineering of the system. In particular it is necessary to specify:
- the learning support “philosophy” (is it directive or not, at the instigation of the trainer or of the learner, at a set or open date, individual or collective?);
- the functions of learning support (educational, administrative, technical, social or psychological guidance);
- the methods (Internet, e.g.: forums, email; letters, telephone, face to face or reassembling);
- the types of communication (synchronous or asynchronous according to the demands of the pedagogical activities);
- the exchanges that are anticipated, encouraged or compulsory between peers, according to what methods (e.g.: reassembling, telephone, forums etc.) pace, directive or not, according to what objectives (e.g.: create a sense of belonging to a group, shared interests, favour learning with others, a team spirit, socialization etc.).
A few recommendations in this respect:
94)	Provide the learner with a tutor with a well-defined role; enable the learner to identify the training manager.
95)	Involve all of the participants as soon as possible (e.g.: control points at regular intervals, monitoring by all of the progress of each person's work).
96)	Promote tools that facilitate the emergence of a community of practice.
97)	Do not fragment, or concentrate all of the roles in a single participant.
98)	For the tutorial system, maintain a balance between reactive and proactive positions, between those focussed on knowledge and those focussed on regulations.
99)	Formalize the roles of each person, with possibilities for development during training (which will then be clearly specified to the learners).
#### Encourage collaboration, sharing and joint construction
100)	Provide for pedagogical approaches promoting mutualization, the need for cognitive exchanges (e.g.: joint work, case studies, sharing of tasks in a project etc.).
101)	Lead these collaborative activities: define an objective, the means, time limits and nature of the task to be achieved, keep up collaboration throughout the process (e.g.: chasing up, synthesis, benefits of new elements, feedback).
102)	Provide the tools for mutualisation: forum, chat, downloading and monitoring space for documents.
103)	Encourage collaboration between learners by effective collaboration between teachers (modelling).
#### Involve the hierarchy of learners
104)	Provide for a tripartite training contract (training institution / learner / hierarchy) to specify in particular:
- allowed training times;
- conditions of access to computers and the network;
- any possible conditions for applying learning within the professional context;
- conditions for monitoring and feedback concerning the progress of the training course;
- the effect of this type of training on skills management.
#### Provide for methods of assessment of learning
105)	Provide for different methods of assessment (e.g.: formative, summative etc.) in order to enable learners to continuously position themselves in their learning and to build up their knowledge as they progress.
106)	Explain clearly the instructions concerning the anticipated tasks and the assessment criteria applied.
107)	Ensure the openness of the tracking of results obtained and access to them by persons other than the learner and his/her tutor.
### Provide for the introduction of quality control
Quality control must be included in the construction stage to enable it to be assessed in accordance with the methods that will be specified in the “Assessment” process.
108)	Draw up a “reference” document specifying the aims, objectives, values and strategic elements of e-learning.
109)	Construct tools to measure:
- pedagogical effectiveness;
- effectiveness of technological tools;
- effectiveness of educational aids;
- the satisfaction of learners and other parties;
- costs per person.
## Construct the pedagogical resources
Pedagogical engineering consists in creating a learning environment that is effective (achievement of educational objectives) and efficient (relevant and profitable). This includes pedagogical division, contents, choice of aids for passing on contents, support activities for learning processes and the resources made available. Creating a learning environment that is effective and efficient consists in using existing resources, in adapting them or if need be in creating them.
We have distinguished the educational aspect of the design of resources from the stage of implementation and IT development which is dealt with in the following process: “Drawing up”.
WARNING — It is often preferable to favour the use (or purchase) of resources that already exist or that can be adapted, before envisaging the creation of specific resources that are more expensive but which may prove indispensable in certain cases.
### Organize the approach
The use of training resources is part of a general system. It is necessary therefore to favour a general view in order to ensure the coherence of the whole system, before plunging into the mass of details that constitute the training resources.
110)	Plan the whole of the programme, check the homogeneity of the sequences proposed, appropriateness to the educational choices and to the initial objectives of the course.
111)	Check the flexibility (non-linear training course depending on requirements, prerequisites, pace and the availability of learners).
112)	Check the coherence of the organization, whatever the type of individual course.
113)	Determine the estimated average length of the training course (overall and by module), in accordance with the educational objectives, the demand, the context (urgent or not), the public and its availability.
114)	Determine the expected production of learners (individual or collective, at a set pace or not, for which educational objectives).
115)	Check the share of contextualization of contents, exercises, simulations and case studies in particular in the context of training courses specific to companies and/or professions.
116)	Check the involvement of the client (learner/sponsor/financier) is taken into account when it has been made explicit (supervision, monitoring).
117)	When the context makes it possible, mutualize experiences and practices during design and construction (pass on and share “good” experience).
### Characterize the pedagogical resources intended for e-learning
The resources must meet the requirements of learners and the contexts of the sponsor.
118)	Take into account the learner’s ability to concentrate and the need to switch continuously between acquisition and verification of acquisition (e.g.: integrate content and check its integration through an exercise or a test).
119)	Segment the content into relatively independent units (granularization) corresponding to learning subjects.
120)	Store the learning subjects in environments such as knowledge and/or learning databases (importance of nomenclature) for use according to public and requirements.
121)	Ensure the simplicity of access to this content, its intelligibility and the quality of the interactivity.
122)	Script the content then “mediatize” it (e.g.: presentation to favour learning then mediatization: images, sounds, videos, colours, photos and graphics). Experience shows that sobriety and simplicity are better than too much animation which can impede acquisition/understanding of contents.
123)	Enable the learner and trainer to check acquisition of content through self-assessments and self-inspections, assessments and exercises or work: clear instructions must be provided for these assessments.
124)	Enable the project manager or a trainer to check the coherence of all contents produced.
But, be warned, excessive atomization of learning subjects may be detrimental to scripting and therefore to learners’ motivation (as was the case with education by objectives). More generally, it is important to reaffirm that the behaviourist model of learning is not the only model. Simulations and problem-solving case studies are appropriate even if they can be difficult to create.
#### Learning support resources and activities
Refreshing/revision of basic notions, exercises/tests to check the progress and standard achieved, simulations, games, improvement, further reading etc. are all activities that support, strengthen and validate the learning processes. Depending on the context, learners can choose them according to their own ways of learning and working.
125)	Devise the support activities as an addition to the learning processes, aimed at specific educational objectives (too many activities or activities that are too varied may make learners lose their concentration).
#### Choose media
The choice of media follows from the educational objectives to be achieved. The final choices are a compromise between organizational, economic, cultural and sometimes legal and human constraints, and the skills and resources available. However, for the marriage of the content and the container to be successful, the educational purpose remains a priority as far as possible.
126)	Demonstrate the advantages of the use of ICT in the implementation of the necessary resources.
127)	Use the experiments already carried out.
#### Decide between use of existing resources and/or creation of new resources
Once the programme has been planned and a synopsis has been made of the different types of pedagogical resources and aids, it is now necessary to mobilize them. Since designing them can be particularly costly (in time, in human resources and in financial resources), before embarking on the creation of new resources it is necessary to:
128)	Locate existing resources on the market and in-house.
129)	Identify the methods of acquisition.
This technology watch allows the following actions.
130)	Proportion the human, financial and technological resources needed to mobilize the necessary pedagogical resources.
131)	Specify the volume, nature and contents of the specific resources to be produced for the project.
132)	Set out the development choices that follow from them: what technological choices, internalization and/or outsourcing of all or part of the tasks.
### Create specific resources
The creation of specific resources is a genuine subproject within the project and includes several subprocesses.
#### Locate existing content
All or part of e-learning may be based on generic contents or the (legal) diversion of resources existing with unrestricted access on the Internet. But before recommending them to future learners it is necessary to carry out the following actions.
133)	Conduct market research to discover the existing offer (generic products existing on the market, diversion of resources with unrestricted access, products developed during previous training courses etc.).
134)	Specify selection criteria (e.g.: pedagogical approach, type of interactivity, technological compatibility, level of improvement, prerequisites, price etc.).
135)	Test these products on a representative sample of the target public.
136)	Design educational structures for integration and for support for their use in the course (e.g.: instructions, explanatory notes, sequencing, assessments etc.).
#### Create a project team
e-learning educational design mobilizes various didactic, pedagogical and technical skills. It is necessary to:
137)	Choose a single project manager, from the analysis of initial requirements to the final delivery, who acts as an interface between all of the parties (sponsors and production team) and coordinates and follows the teams.
138)	Gather together a multidisciplinary team (subject, pedagogical and technological skills, human resources and communications managers).
139)	Design and develop contents using a collaborative work approach involving in addition the maximum number of trainers concerned by the implementation of the training course (e.g.: management of change, overcoming resistance, appropriation of the products produced).
Nevertheless, in the face of the difficulty of implementing two different professional logics and the importance of not dissociating the design of the content from that of the container, institutions recommend that the technicians should also be trainers, others that the trainers should be trained in the technology or even better, that the project should have a project manager possessing both abilities and capable of acting as a mediator between these two professional logics.
#### Respect the different stages of resource design
The creation of training resources involves several stages. This has become considerably more professional in recent years in particular with the convergence of the IT and audiovisual professions.
Two main stages can be identified: scripting and mediatization according to the technical choices (e.g.: availability of media such as sound, video, animation etc.).

Scripting of knowledge
The scriptwriter will present the knowledge by finding the right balance between:
- teaching aspects (content);
- learning models chosen according to educational intentions;
- the type of circulation and interactivity;
- technical and financial constraints and possibilities;
- drawing up of synopses of the content.
To begin with (s)he will then compose the synopsis.
It is at this stage that it is necessary to reconcile the often contradictory qualities of creativity, similar to stage or cinema production, and the extreme rigour of formalization in order to enable subsequent IT implementation. Only a team makes it possible to ensure this combination of rigour and creativity.
In all cases it is necessary to go about things in stages and to validate each stage immediately after its completion. Indeed, the main risk to be avoided consists in designing and then creating the whole of a resource, only to realize its technical inadequacy and/or inadequacy in terms of contents and having to start the production again from scratch, with the consequences that can be imagined on time limits and production costs.

140)	Form the corpus to be scripted and have it validated by the content experts.
141)	Think out the educational approach for the contents to be scripted according to pedagogical intentions (more inductive approach where the intellectual activity of learners is put to greater use in some cases, tutorial approach in other cases).
142)	Model, organize and prioritize training subjects and objectives.
143)	Write the story-boards making sure that you alternate the different cognitive activities (e.g.: search for information, memorization, analysis, assessment etc.).
144)	Assess throughout the design stage.

Mediatization
145)	Define a common graphic charter in order to favour the conceptual and graphic harmonization of the contents produced.
146)	Optimize use of the different media according to their specificity and their ability to reinforce each other.
147)	Carry out validation of the prototype from a technical, ergonomic and educational viewpoint.
### Provide for distribution
During this stage the project is finalized and will be delivered to the client (learner, sponsor, financier) and implemented.
148)	Check once again that legal and financial constraints have been respected.
149)	Share out tasks, plan and organize to ensure that the system functions (procedures for creating lessons, updating, correcting mistakes, support etc.).
150)	Check the logistics (postal items, management of the computer network and hardware, publishing, printing, maintenance, management of equipment malfunctions etc.).
151)	Ensure that the (current or new) facilities are operational to produce and distribute the contents and maintain quality.
152)	Create initiatives for internal communications (in-house launch and development of the course), and external communications (advertisements, editorial advertisements etc.).
153)	Ensure the conditions of transfer in the event of subcontracting (communications, appropriation stage, compatibility with existing facilities).
# Equipment stage
## Specificity of the process
Technology is the basic element of all E-learning systems involving the use of ICT. This technological dimension is included therefore from the time of the preliminary analysis and construction of the system. The aim of this code of practice is not to replace the expertise required, but to comprehend the question of the viewpoint of the decision-makers and users directly concerned. It is necessary to describe in terms of a process how the technological dimension of e-learning can be taken into account, in order to put forward a certain number of recommendations to optimize the integration of the equipment process in a coherent e-learning approach.
### A systemic approach
The introduction of technology into a standard training system certainly makes it more complex, which requires continuous rigour and vigilance in the implementation and maintenance of the system. Technological failure or dysfunctions may go so far as to prevent the completion of the learning processes (delay in distribution of the courses, connection impossible or too expensive, schedule of telephone guidance or for access to synchronous activities incompatible with professional and family life). Contrary to standard training situations where compromises can be reached, the distance and/or possible absence of a trainer leads to a situation with only two possible outcomes: either it works or it doesn’t.
The complexity comes from purely technical aspects, but also from the following characteristics:
- the diversity of the parties (learners, trainers, tutors, technicians, contractors, financiers etc.) who intervene in this data processing chain;
- the level of technological skill of these parties is often mixed;
- the technologies are very upgradeable (operating system, office automation software, educational software, networks, telecommunications);
- the difficulty of prioritizing and then making the technical choices while clearly following managerial and financial priorities;
- the ongoing implementation of media technologies, whether sophisticated or not, requires production, maintenance and services organizations that are unusual in training.
It is particularly difficult to take into account this systemic dimension for training operators who are not used to evolving in the context of the information system of a large organization.
### Technological determinism or pedagogical primacy
Technology reveals an often insurmountable tension between training professionals, who claim the primacy of educational aspects, and IT professionals who recommend a certain technological determinism. For the former, technology only represents an extension, subordinate to educational intentions, learning, the learners, innovations etc. For the latter, the integration of training technologies is part of a wider issue concerning the development of information systems internal and external to the organizations (companies and administrations). Depending on the context, the criteria for making a decision depend on the technical interoperability, the convergence of systems in terms of prospects of governance of the information systems and/or a concern to reduce management costs of information systems.
### Technology as a factor for differentiation
Technology is included in training systems not only according to the training requirements, profiles and objectives of the learners, but also according to the available infrastructure, the logistic organization and the statutory and budget constraints. These parameters vary according to the characteristics of each type of training operator.
It is necessary to carry out this essential contextualisation to make the technological choices suited to the specific issues involved and its positioning in the social context of training: mass training and training of small numbers, a training structure that is isolated or in a network etc.
The development of networks and in particular of the Internet should facilitate access to the training system, even if in practice there are often obstacles that are difficult to overcome for reasons linked to the technology, according:
• either to social inequalities (e.g. for job seekers) and/or problems linked to area (access to broadband in the country);
• or to accessibility to the equipment and/or the network (clearance) in large organizations for reasons of IT security and cost.
In the medium term it is likely that we will see ICT becoming more commonplace and progressively integrated in standard training activities.
Paradoxically, for distance operators, the introduction of ICT brings the operator closer to its customers. It makes it possible to personalize a mass training offer, to reduce response times for the correction of exercises, practicals etc. and to reduce the management costs of traditional logistics (postage, duplication etc.) by transfer to the user.
The equipment stage can be broken up into 4 subprocesses:
• necessary choices of technology;
• implementation or “deployment”;
• maintenance of the technical systems;
• development of selected solutions.
## Choosing
Choices of technology are particularly delicate and must be the result of decisions of a strategic nature. They involve the quality of the training system and often result in transformations in varying degrees of former work procedures and organization. As a result, although these technological aspects clearly concern the technical department within the organization, these choices are the responsibility of the senior management. In large organizations which already have one or several information systems it is often the IT department that controls these increasingly complex procedures, sometimes to the detriment of the training departments.
Intended to provide decision support, the direct opposite of ready-made solutions that are totally unrealistic considering the diversity of situations and the rapid development of technology, this CoP specify the stages to be respected and provide a few qualitative orientations making it possible to choose according to key criteria.
The response to these questions also provides help in reaching a decision on the human and financial resources required, whether it involves solutions within the organization or outsourcing.
### Create criteria for the choices
#### Human resources-type criteria
We favour here cross-disciplinary and generic aspects.
154)	Have a good understanding of internal skills: architecture and network skills since the facilities are forced to develop in a way that is sometimes significant, and/or internal development skills.
155)	Ensure cultural integration: a tool that is too complex or too unfamiliar to the corporate culture, or to that of learners or teachers will interfere with the learning processes (the working environment of the learner must be simple and easy to use); choose a basic tool which will be quickly integrated and valued by users, and gradually move to more complex tools.
156)	Check the ease of use: check the equipment and the level of familiarization and solutions for “non-equipped” parties; clarify the criteria for choice (flexibility, individual interventions, security, compatibility with existing tools, expected functions, cost, time required for implementation) and share them with all of the participants/future users.
#### Criteria linked to tools
These criteria are linked to the tools themselves, regardless of the organizations in which they will be integrated, but it is necessary to emphasize the importance of analyzing what already exists in terms of facilities which will make it possible to assess the adjustments to be made for optimum use of the applications.
157)	Ensure continuity: this is the main criterion if it involves producing resources that are reusable over several training cycles (unlike “disposable” resources such as the transfer to the euro for example, which only have a lifetime of a few months). The choice of a well-known brand may provide reassurance but no absolute guarantee is possible in this area (if we take the example of the authoring languages of the bygone days of DOS, not a single system has survived the transition to Windows…).
158)	Ensure upgradeability: the tool chosen must also be upgradeable according to uses, practices and requirements.
159)	Make sure of the interoperability and check its operational nature (this criterion is fundamental as it determines the circulation and permanence of the choices) by controlling for example:
- the compatibility of video files for example (currently 3 competing standard formats);
- the possibility of recovering in a mixed technical context the scores obtained by multiple choice question generators.
### Observe a few conditions
These choices are essential as they will have lasting consequences.
160)	Bring together as much information as possible for all potential users (requirements, level of expertise) and technology experts.
161)	Use the results of competitive intelligence.
162)	Take into account cross reference charts on the Web.
163)	Consult specialized newsrooms.
164)	Possibly secure the aid of a consultant.
165)	Make sure of the coherence of the investment in a platform with strategic analysis (importance of a multilingual federative tool, priority of the creation and/or purchase of contents etc.).
166)	Decide between hosting the solution or renting it in ASP mode: the number of learners and the length of the operation often determines this choice when it really depends on the training course. In large organizations this choice is generally the responsibility of the IT department.
### In-house or outsourcing
This question arises for large projects in particular.
167)	Remain focussed on your core profession and hire contractors for specific services.
168)	For subcontracting, it is useful to have previous experience, to avoid exposing yourself to serious difficulties.
169)	Provide extremely rigorous monitoring. It is sometimes difficult to exercise this rigour in-house.
170)	Determine a reference organization model, specifying on the one hand the respective responsibilities of the project manager and of the prime contractor and on the other hand those of the producer and of the executive producer.
171)	Specify what is required to avoid amendments and ensure that the budget and schedule are respected.
Criteria for choosing contractors:
172)	Choose a contractor who offers the best reactivity and flexibility.
173)	Choose a company with sufficient experience and references in the market.
174)	Ask for references of projects and make sure that they are not just prototypes.
175)	Contact the project managers of the customer references directly.
176)	Check the pedagogical and technical skills of the future contractor by carefully examining the references and products already produced, or by financing the creation of prototypes.
## Implementation
### Buying
When a purchase is necessary, whether for small structures or large organizations, the expected functionalities and characteristics must be clear.
177)	Formalize the expected specifications in a specifications sheet before choosing the tool (and not the reverse).
178)	Ask the supplier for a real example (subject to respecting confidentiality) rather than a demonstration to judge performance.
179)	Take into account the possibility of adapting the solutions and services proposed.
180)	Provide for a test stage in a real context before confirming the purchase.
181)	Find out about the costs and methods of maintenance and updating.
182)	If a purchasing department is involved, make sure that the procedure is followed up to avoid misunderstandings concerning the “best offer”.
183)	Make sure that there is the right balance between technical and financial criteria in decision models for calls for tenders.
184)	If necessary take part in the commissions for sorting calls for tenders.
### Use free software
This is a sensitive issue on which it is currently difficult to reach a consensus. Without taking sides, we can however consider that it involves realistically choosing between two conflicting economic models: paying a software editor to use turnkey solutions, or using free software and providing for internal and/or external advice and support.
The use of free software may reduce the cost of the system. It is necessary however to respect a few rules, in particular to check on the one hand the reality of free use of the software in the event that you decide to use it, and on the other hand its permanence, particularly in keeping up with the development of operating systems.
### “Tailor-made” solutions
Difficulties arise in terms of the definition of requirements and creation of the different modules needed. Creation may involve a genuine subproject within the project.
185)	Draw up detailed specifications.
186)	Estimate the workload and time limit for completion.
187)	Provide for tests from the launch of development.
### Deployment
The implementation of the technologies selected follows standard approaches for the deployment of information systems.
188)	Think ahead: inform the main persons concerned sufficiently early, announce the reasons for the choices and the positive effects expected. This information favours the involvement of the parties.
189)	Synchronize: Too big a gap between the information or the prior training and the deployment of the technical solutions generally causes a heavy loss or despondency among those concerned.
190)	Provide support: the implementation of e-learning tools requires rigorous support in particular during the first days. Dysfunctions generally appear right at the start of the operations.
## Provide maintenance
Maintenance is an integral part of the “Equipment" process. The technological dimension of the process requires that this subprocess to be included in all e-learning projects both in terms of inclusion in the budget, and of the skill required, whether the activity is provided in-house or outsourced.
### Distinguish preventive maintenance from curative maintenance
191)	Favour preventive maintenance: it is the most effective since it anticipates problems but its relatively high cost implies prioritizing sensitive maintenance areas to concentrate this type of maintenance on the key points.
192)	Nevertheless, provide for curative maintenance: it remains essential as it intervenes on the spot. It can be costly both financially and in terms of the motivation of the different parties concerned.
### Maintenance areas
#### Computer population
The obsolescence of computer populations is a recurrent problem of e-learning activities.
193)	Compare the different solutions on the market: purchase, hire-purchase, hire.
194)	Adapt the maintenance solutions to the specificity of the computer population: quantity, dispersion, homogeneity / heterogeneousness.
195)	Make lasting choices: 3 to 5 years in general.
#### Application-type software
The technical environment may be changeable: change of communications protocol, change of operating system (transition to Windows XP or Linux for example).
196)	Provide ongoing monitoring of the solutions proposed.
197)	Budget for the cost of updating strategic software.
198)	Make sure of the existence of an efficient hot line in terms of reactivity and competence at acceptable costs.
BP Z 76-001
#### Training resources
199)	Specify the “disposable” resources which, like the preparation for the transfer to the euro, are produced and distributed on an ad hoc basis, from the stable contents which constitute the heart of the training structure.
200)	Upgrading these resources may prove to be vital for the operation of the systems: this requires traceability of the resources which relates to documentary techniques.
These resources which represent a genuine intangible capital for training providers, are precious and it is necessary to enable them to be updated regularly and to be accessed from different software environments.
201)	Index: updating training resources involves introducing a reliable and exhaustive system of indexing digital documents.
202)	Document: indexing is necessary but inadequate to provide maintenance of resources without comments on the contents indicating the key points.
203)	Revise regularly: lack of revision of training contents may result in the loss of credibility of the entire system (e.g. a VAT rate that is not updated may undermine the credibility of the entire course).
## Develop
The continuing development of technological solutions is one of the most difficult factors to include in an e-learning policy since it is in conflict with the relative stability of the methods and practices implemented in training course engineering. While favouring permanence as the decisive criterion, it is necessary to accept the prospect of a possible reappraisal (total or partial) of these choices every 18 to 24 months.
Since this context creates uncertainties, it is important to think ahead.
204)	Try to reduce the negative effects of this uncertainty through ongoing techno-watch.
205)	Exchange information through shared practice in order to clarify the issues and then the possible operational consequences of these reappraisals.
### Centralize operations
It is important to centralize, especially for multi-site institutions.
206)	Guarantee the coherence of choices of technology.
207)	Reduce costs by avoiding multiplication of “specific” tools and take advantage of scale economies.
208)	Mutualize “good practice” to choose the right tools.
209)	Provide for the development of tools according to new requirements that emerge (from learners, trainers, administrative managers).
210)	Provide Provide for the training of participants in use of the new tools.
### Provide techno-watch
Techno-watch is therefore one of the essential and fundamental tasks. This does not mean that all decision-makers must become specialists in the techniques of multimedia and/or Internet production, but that it is essential to express the technical questions in terms of educational and financial issues, in order to take the necessary decisions.
211)	Beware of one-off methods and solutions: indeed, Internet alone is not necessarily the one and only answer to all our needs. More standard solutions in resource centres, such as the use of CD-ROMs or other methods that can be devised should not be neglected.
212)	Mutualize certain aspects of the techno-watch: techno-watch is becoming more and more complex and its cost is often prohibitive for small and medium-sized organizations. The exchange and sharing of information through an organized network also make it possible to make up for the impression of isolation often experienced by participants in the training course.

# Conducting the training course
## Specificity of the process
The learner is one of the main participants in this process, during which the aim of all training systems is achieved: learning. Learning is therefore at the centre of all of the practices described in this section. In addition, conducting e-learning may be distinguished from conducting a traditional training course in at least two ways: the partial desynchronization of relations between the learner and the trainer(s) and the polymorphism of the approach.
The partial desynchronization of relations between the learner and the trainer(s):
In face-to-face instruction the tutor has various indicators that make it possible not only to assess the impact of his/her mediation on the learner, but also to instantly correct any weakening in attention, any failure to understand, or reactions to the teaching. In distance learning these spontaneous indicators no longer exist and it is essential to invent new ones and to reach a compromise concerning the inevitably longer period of time between a warning or request for assistance being voiced, and a solution being found.
The polymorphism of the approach involves more varied situations which are led by a greater number of people, professionals with various roles and duties that need to be clarified. The “one-man band” role of tutors in face-to-face instruction is replaced by a form of polyphony, in which the other learners also have a new and unique role in supporting individual learning.
The training course may be a combination of these different situations, in a way that is free or imposed. Without being tailored to individual needs the training course may offer predefined differentiated courses. In this case, these must be explicitly described, and all of the elements making it possible to make the most appropriate choice must be provided (e.g.: ability test, interview etc.).
## Joining the training course
### Information and adherence to the project
Even more than in standard training courses, the success of E-learning depends on the learner’s support for the training project (content and methods) that is proposed. For in-house training, this adherence will also extend to the working environment (particularly the level of the immediate superior of the learner). There will be all the more commitment to the training project since the learner and his/her superiors have the necessary information, since they have been involved in the construction of the methods implemented (tailoring to individual needs), since all of these methods have been worked out in consultation with all of the parties involved (comprehensive consultation) and since these methods have been explicitly drawn up.
Before joining an e-learning project, the learner should have the information needed to be certain that the training proposed actually corresponds to his/her personal objectives, that the methods implemented fit in with his/her professional and/or personal constraints, and that the training provider is worthy of his/her trust. In this context it is important to provide access to all of the information concerning both the training offer in question and concerning the training institution which proves its credibility and its ability to provide a quality service.
213)	In addition to the standard information relating to the offer (c.f. standard NF X 50-760) clarify the following points:
- the objectives of the training course (subjects, skills or abilities aimed at and expected levels of expertise), as well as the ways that these will be verified and validated;
- modularization of the training course (division into units and topics etc.);
- the educational model (e.g.: transmissive, appropriative, case studies etc.), which will be explained to the learner in comprehensible and possibly illustrated terms;
- estimate of the total length of the training course and the length of each module or sequence; this average length will be based on learning time (versus teaching time) and will include times allowed for personal work needed to carry out all of the tasks;
- the experience of the training provider as regards e-learning.
### Development of a course tailored to individual needs
Tailoring learning to individual needs is not peculiar to e-learning, but the advantage of e-learning is that it not only makes it possible on a large scale, but also makes it almost indispensable in order to meet the expectations of learners and their prescribers for a “just in time and just enough” approach. This tailoring to individual needs can take different forms: tailoring of courses (e.g.: differentiated courses according to individual objectives and prerequisites), of methods (e.g.: tools, length, nature of the learning support) but also of the contents or even of the possible pedagogical approaches (e.g.: inductive, deductive, simulations etc.).
Tailoring to individual needs obviously does not rule out group sessions.
Tailoring to individual needs consists therefore in constructing a personalized course according to different criteria which may be more or less combined. These criteria are specified to the different parties concerned (e.g.: financiers, learners etc.).
A training course tailored to individual needs may take into account all or some of the following criteria:
- the prerequisites of the learner;
- objectives pursued;
- validation method (leading to a qualification or not);
- learning style;
- pace;
- length of the training course;
- the pedagogical model implemented;
- preferred method of guidance.
In drawing up the course it is advisable to implement the following actions.
214)	Make sure that the facilities available are suitable for the pedagogical activities proposed.
215)	Take into account the availability of the places and of the learner in the structure of the different “moments” of the training course.
216)	Ensure the principle of continuity is respected, so that the learner finds the same work environment wherever study is carried out.
217)	Plan to give the learner the means to identify clearly areas of freedom and “requirements” inherent in the course.
In addition is should be noted that e-learning may be followed in different places (home, resource centre, work station) and at different times (e.g.: partly during working hours, partly during spare time at the resource centre, partly at home). Choice of the training place(s) and time(s) must be made in consultation with the learner and the participants facilitating his/her access to the training course (e.g.: leader of the access point to distance learning, superiors of the learner in the company, resource centre manager etc.).
218)	As regards tailoring of areas / times, take the following into account:
- intrinsic contingency of the training course (in particular for professional software);
- availability of and accessibility to suitable equipment (e.g.: computer, broadband connections etc.);
- legal aspects of the training course;
- personal situation and requirements of the learner.
### The personal training contract
This personal training contract (sometimes called personal training agreement) systematically specifies and formalizes all of the methods of the service implemented with the learner in question. It is signed at the end of the information and construction stages of the personalized course that were carried out previously. It specifies the commitments, responsibilities, rights and obligations of each party in the implementation of the course.
The personal training contract provides for the parties, the actions and the methods of the training course.
219)	Involve as many contracting parties as there are entities or parties in the implementation of the training course. In its simplest form, this contract concerns the learner and the institution that provides e-learning (in the event that the learner is his/her own training financier and prescriber). But it also involves the institution to which the learner belongs, in the event that the training course is carried out under its responsibility and that it has the role of facilitator of access to the training course (e.g.: time allowed, reserved areas, provision of software solutions). Specify particularly the pedagogical (heart of the contract) and financial aspects, which can take the form of an agreement.
220)	Its clauses must cover the organizational, pedagogical, technical, legal and financial aspects of the course in question, together with the rights, obligations and recourse of each party for these different aspects.
221)	Include as many “educational sections” as there are different subjects to study.
222)	Provide for methods of renegotiation: since it is impossible to predict the way in which the learner will progress during the course, it is advisable to make provision for times when methods of modification (e.g.: of pace or even of tutor etc.) will be possible.
### The appropriation of the new learning environment
The learner must appropriate the new learning environment. It is essential in fact that (s)he should be at ease with the learning tools and environments that will be proposed. This pre-training and accompanied adaptation stage, based on the specific requirements of the learner, enable him/her to understand the functioning of the new learning environments, to acquire points of reference and to identify the roles and duties of each party.
223)	Take into account the technical aspects (e.g.: platform, tools etc.) and their use by the learner (in practice more than in demonstration etc.) in his/her final learning environment.
224)	Take into account the methodological and organizational aspects (e.g.: time management, organization of the work into sub-groups, appropriation of the communications methods and technologies, return of assessments, people to refer to etc.).
225)	Take into account the behavioural aspects in the new environment (e.g.: protection of personal data, correct use of tools, code of good practice, netiquette etc.).
## Provide support
Distancing (geographical, temporal and social) of all or part of the training course does not remove the need for a socio-affective relationship, which is essential for the implementation of a learning activity. This support, the aim of which is to facilitate learning processes by taking care of the cognitive, organizational, technical, social and psychological requirements of the learner, assumes very different methods and means of implementation depending on the system.
### Types of learning support
In e-learning, the learner must be able to call on different types of learning support combined.
Learning support focuses on:
- educational aspects (e.g.: monitoring and guidance for progress) this involves facilitating distance learning by taking into account personal factors of autonomy, management of space and time, possible management of the stress that e-learning may cause among certain learners;
- didactic aspects (e.g.: expertise linked to the area of competence and/or of knowledge);
- methodological aspects (for example help with organization, with solving problems);
- technical aspects (for example solving problems linked to technical environments);
- administrative aspects (formalities for a training period, the problem of social security cover, illness etc.);
- relational aspects (for example leadership of a peer group, the moderator etc.).: psychological support, remotivation, encouragement, coaching, personal advice …the Canadians also speak of “social support”: managing one’s training in relation to one’s work, one’s family, health problems etc. In e-learning all of these factors have a direct effect on training, unlike in face-to-face instruction, and represent significant causes of withdrawal and failure.
Depending on the system (its length, volume, complexity, pedagogical approach, the face-to-face / distance ratios etc.), these support requirements are provided for by a team the composition of which attempts to meet as effectively as possible the requirements and constraints of the various parties.
In terms of learning support skills
226)	Clarify the roles, duties and type of guidance provided by each of these contributors, as well as their methods of intervention and questioning by the learner (e.g. mentioned in a guidance charter).
227)	Formalize and communicate to the learners the area of responsibility of each party, should the course involve different institutions (programmes given by a consortium or in partnership between online training provider and local access point, for example).
228)	Make sure that the skills and abilities of the tutors are appropriate for their missions.
229)	In the event of learning support provided by numerous people or entities, provide for a system of regulation and coordination between contributors: supervision of tutors providing the role of monitoring, inspection and mediation between tutors and between tutors and learners.
230)	Make sure that the roles and missions of all concerned are not altered unilaterally during the training course (e.g.: establish checkpoints to avoid abuse). For all that, if adjustments must be made, which is natural in a long course, these must be explicit and methodical.
### Monitoring tools and methods
The different types of learning support are based on different tools or face-to-face/distance situations: methodological support at the resource centre, telephone interview (on the initiative of the learner or trainer), chats, email, videoconference, remote control of the work station, hot line, FAQ file etc. Each of these tools meets specific learning support requirements and lends itself to well-defined educational intentions. They can be used indiscriminately throughout the course or on the contrary at specific times (the hot line for example is very useful at the start of the training course).
Concerning monitoring tools and methods
231)	Choose the method of communication the most appropriate for the intended educational use (coherence of content and form).
232)	Make sure that each learner has – or acquires – command of the tools and has the required IT skills.
233)	Make sure that each learner has the possibility of having a suitable work environment.
234)	Clarify the rules for each type of interaction, each medium and each type of guidance. For example, a question asked by email must receive a reply within 48 hours; monitoring meetings are arranged in advance etc.
235)	Leave monitoring as much to the initiative of the learner as of the trainer. For example failure by the learner to respect deadlines becomes a warning signal that the trainer must treat as such by chasing up the learner.
236)	Implement methods of tracing these tutor/learner relations, and of reporting information between institutions so as to maintain monitoring of all learner-trainer interactions.
237)	Ensure the permanence of the educational service: in the event that a commitment could not be honoured by the team of trainers, the learners must be informed; if a student asks a question to a tutor who is not able to reply, the request must nevertheless be taken into account and passed on.
## Favour collaborative distance work
Collaborative or cooperative work is not an absolute requirement for e-learning. However in a good many cases it may provide a solution to learners’ isolation and provide support for their motivation through the sense of belonging that it creates. These asynchronous or synchronous group relations will be more or less organized and will have tools to achieve the educational aims that are expected of them: social cohesion, sharing of knowledge or the production of knowledge.
Three scenarios are possible:
- the relation between peers is limited to making available tools for communication between learners, mainly for the purpose of social interaction;
- the mutualization and sharing of knowledge within the community are part of the pedagogical strategy and support the individual activities, the objective being to re-create, in this case, group situations thanks to synchronous (e.g. chat, videoconference, virtual classrooms) or asynchronous (e.g. forum) tools;
- collaborative work may also be selected as the founding educational principle of e-learning in question, and in this case the main part of the learning activity will involve collective distance production and must be supported by the tools but also by the methodological and motivating support needed (e.g. a clear definition of the objectives, leadership of the community, final and intermediate syntheses).
Concerning the organization of relations between peers during learning
238)	Use the technological methods which are the most appropriate for their intended use.
239)	If the collaborative method is selected, create the conditions for it to be produced, e.g. by stimulating group dynamics at the start of the training course and by proposing certain activities during the training course in which learners are encouraged to exchange ideas.
240)	Provide for the leadership of the different production and/or exchange areas and the rules of this leadership; specific positions dedicated to this role (e.g. webmaster, moderator etc.) are essential.
241)	Implement a confidentiality clause in which learners undertake not to pass on information from the other trainees without their consent. This confidentiality charter must also be signed by the tutors/trainers who also undertake not to pass on sensitive information to third parties.
242)	{0>Sensibiliser à la netiquette (par exemple :<}0{>Make users sensitive to netiquette (e.g.:<0} {0>règle de courtoisie dans l’écriture électronique).<}0{>rule of courtesy in electronic writing).
## Validation of learning
To support times of self-training during distancing of learning, e-learning requires methods of assessment that are more formalized than traditional training (e.g. assessment of self-assessment, formative assessments, summative evaluations etc.), different types of assessment that technologies make it possible to equip and rationalize. Thanks to these new methods of assessment learners can assess their position within the course and in relation to other learners (those of their learning community or those who have carried out the course before).
Concerning assessment and validation of learning
243)	Give the assessment processes a substantial share of the learning process.
244)	Have this assessment process validated when the learning contract is signed.
245)	Punctuate the training course with formative assessments to enable continual self-regulation.
246)	Introduce non coercive assessments to help the learner to carry out self-assessment of learning.
247)	Introduce explicit indicators for the minimum, average and maximum progress of all of the learners, so that each person can assess his/her position.
# Assessment
## Specificity of the process
E-learning are the subject of substantial investments at all levels (political, economic, organizational and human). The stakes involved in e-learning put it in the front line in terms of expectations, requirements and still sometimes of fears or reservations. This context explains the risk, in terms of assessment, of “extremism”, since it can be noted that the level of requirements as regards assessment of E-learning is much higher than for more traditional training practices.
This requirement can be explained by some of its specificities: size of the necessary investments, technical means of traceability, or even the need for innovative practices to prove themselves etc. This strengthens the role of the assessment process as a factor for regulating and deciding between realistic and unrealistic expectations concerning the effects of e-learning.
This process proves therefore to be the most delicate to work out, at least in use.
In more concrete terms, without assessment it is not possible:
- to assess and differentiate the elements of success of e-learning;
- to optimize the result or to regulate during the implementation of the project;
- to objectively establish choices for reorientation or renewal of the system;
- to identify the real impact of ICT, alone or in combination with other elements of the system, on uses and results for the learners, for the training institution, the financiers, the trainers, etc.
### Explanation of the issues
Prior to the training course, the main objective of the “Assessment” process is to measure the degree of implementation of the different levels of objectives specified in the preliminary analysis by measuring the differences between the stated objective and the actual implementation.
The renewal, the permanence or the general use of the system will depend on this assessment. In addition it will start a corrective action plan intended to make it more effective. This objective of improvement fully justifies assessment in e-learning.
This explanation both of the issues and of the purpose of the assessment takes place prior to the training course or the system. It is often considered to be obvious, but quite rarely formalized. This formalization of the different levels of involvement constitutes the first element in the assessment process.
### Traceability of the training activities
ICT make it possible to automate and systematize many of the procedures for the identification of learners and the traceability of training activities. These possibilities open up significant prospects but create new obligations as regards the ethics of data processing:
- consultation of the French data protection watchdog (CNIL) may be envisaged concerning the rules and common practice as regards use of personal information[4];
  [4] The project of a single identifier has mobilized French representatives in ISO negotiations on e-learning.
- traceability (who has done what and for how long?) will also be the subject of special attention as regards both isolated individuals and social partners in large organizations;
- the integration of information relating to training in integrated management of companies' human resources (as can be seen with the development of integrated management software packages) and more widely the convergence between skills management and knowledge management opens up prospects and asks new questions.
### Economic assessment
The development of e-learning also requires a change of paradigm in terms of economic assessment: how to get out of the logic of expenses and statutory imputability and stimulate a logic of investment. This mainly involves moving from budgetary accounting (using up the budget) to a management activity: assessing the breakeven point of a system.
Cost analysis becomes one of the priority areas of the process.
We can identify three subprocesses:
- design and parameterize the assessment;
- collect and analyse the data;
- improve the system.
## Design and parameterize
### Define the scope of assessment
It is necessary to contextualize what one wants to assess by defining the scope of the assessment according to the specificity of the system. Depending on the context, the assessment may be carried out for the sponsor, for the learners or in-house to assess the impact of the e-learning initiative on organization, working methods, skills etc. In any case, make sure that the aims of the assessment are clear and explicit.
The “Assessment” process will take different forms depending on whether it involves experimentation or an action that is in general use and permanent.
Beyond the “common law” aspects valid for all training systems, we will particularly focus on the following specific aspects.
248)	Clarify:
- the institutional policy, including e-learning, in relation to the internal and external environment;
- conducting of the project;
- educational specificities;
- aspects linked to ICT used;
- aspects linked to the skills of participants and to the organizations;
- costs and economic aspects.
249)	Specify the assessment criteria taking into account its systemic character. It is only possible to assess criteria that have already been explained and formalized to a minimum degree. Assessment consists therefore in identifying the existence or not of an explicit criterion, followed possibly by a qualitative and/or quantitative assessment of the performance achieved:
- coherence of the elements of e-learning (conduct the project and focus it on the customer etc.) ;
- effectiveness of the partnership and/or of the subcontracting;
- effectiveness of the training course (success of the learners);
- effectiveness of the technologies used (educational value added, absence of incidents etc.) ;
- rationalization of costs (budgeted costs/actual costs recorded);
- dynamics of transfer and general use.
250)	Define the methods and techniques of assessment:
- type of assessment during and at the end of training;
- participants in the assessment (by internal or external contributors).
251)	Specify the nature and form of the output data of the assessment.
### Specify the criteria
The terminology usually distinguishes the assessment from the audit. In both cases we start from a common definition:
The action of assessing, with the help of previously defined criteria, the achievement of the educational and training objectives of a training initiative. This assessment can be carried out at different times, by different participants (trainee, trainer, client company etc.). We may distinguish for example the assessment of satisfaction, assessment of the content of the training initiative, assessment of learning, and assessment of possible transfers to the work situation (cf NF X 50-750).
Unlike assessment, audit has an exhaustive nature and requires the intervention of an independent third party. In the context of this code of practice, without ruling out audit possibilities, we are concerned with the assessment of the effects of e-learning.
The chart given below groups together in an overall way, the means of assessment, the target, the criteria and the techniques suggested for each of the processes. This does not mean under any circumstances that this code of practice suggests that the assessment should be systematized, but that the specified assessment points should be clarified.
Assessment grid / Process 	Aims	Targets	Criteria	Techniques
Analysis stage	- coherence in relation to the aims and objectives of the participants / - balance between skills/requirements of the project	-sponsors or financiers / - managers / - learners	- operative nature of the partnerships / - rationalization of costs / - conformity with aims and expectations	- analysis of documents / - interviews / - analysis grid
Construction stage	- conducting of the project / - adjustment of resources to learners’ characteristics / - adjustment of the system to the constraints of the participants	- learners / - designers / - trainers	- acceptance by the participants / - navigation through resources / - educational effectiveness / - monitoring of the elements of the contract	- satisfaction rating / - log books / - iterative approach
Drawing up stage	- acceptability of tools / - usability of tools / - ergonomic quality / - technical reliability of the platform	- learners / - trainers / - content producers / - technicians	- effectiveness of technologies used / - accessibility	- tests of prototypes, / - questionnaire / interview / - statements of the difficulties of learners and trainers/producers / - statistics of connection times,
Conducting the training course	- adherence / - co-management / - Adjustment of the service to learners' requirements and method of learning	- learners / - tutors	- quality of formalization tools / - speed and relevance of adjustments to the course / - actual use of collaborative work systems	- identification of critical cases / - recovery of experience (REX) / - analysis of mistakes / - contributions to forums etc. / - assessment of learning / - attendance rate at exams / - dropout rate / - number of “calls for help”

## Collection and analysis
The collection of assessment data is not specific to e-learning. However the means of automation of certain data provided by training management software, concerning connection times and frequencies (which may be more or less detailed), circulation, mistakes, scores obtained etc. open up considerable prospects by systematizing traceability.
The risk of getting bogged down in details is considerable! The remedy is mainly to respect the parametering stage of the assessment by contextualizing the methods of collection according to the objectives assigned to this assessment.
Data analysis, as in any systemic approach, is carried out in all processes, which are dealt with one after another for the sake of simplicity.
### Analyse the strategic results
#### In terms of strategic analysis
It is necessary to make sure that the strategic issues have not been neglected: acquire a competitive advantage, mutualize human and financial resources and develop an offer that uses the specificities of ICT etc.
For decision-makers it is necessary to define the area of assessment of this strategic analysis with the following outlook:
• do better and/or more with the same means;
• investigate news ways of offering training services.
Note the difficulty of bringing together recommendations in a register when there is great diversity of situations and issues. One can only content oneself with insisting on the capacity for analysing the issues, and then for making decisions according to a list of priorities peculiar to each organization.
252)	Favour possibilities for partnership for all or part of an operation (arrangement, geographical cover etc.).
#### In terms of feasibility study
Assessment consists in making sure, using common sense, that under the pretext of innovation the rudiments of instruction design have not been neglected, to avoid the resounding failures that fascination with technology has sometimes caused in the past.
253)	Check the existence of genuine analysis of demand (target population, aim etc.).
254)	Analyse the strengths and weaknesses of the institution.
255)	Analyse the short and/or medium term costs and profitability.
256)	Clarify the decision criteria accepted.
#### Decision criteria
The introduction of ICT and the development of e-learning take time: it is pointless therefore to hope to “hit winners” in this field. A development strategy is believed to take between 3 and 5 years to bear fruit.
257)	Diagnose in depth the strengths and weaknesses of the organization owing to the cultural changes that e-learning involves (desynchronization, investment logic etc.).
### Analyse the construction stage
To a great extent the assessment of this stage is specific to e-learning: choices of technology, mobilization of digital resources, and adaptation of the engineering to personalization and to distance learning. However it is mainly a question of a qualitative assessment which in management terms is a matter for decision-making, and for compromise between the ambition of a project and the financial and technical constraints.
#### Coherence of the system in relation to the target population
258)	Assess the possible difference between the target population and the population actually received in the training course.
259)	Assess the difference between the contributions expected and the effects obtained.
#### Assess the pedagogical resources
Assessment of resources is not an end in itself, the level of methodological sophistication currently achieved must not make us forget the purpose of this assessment. Before introducing assessment of resources, ask yourself the question: what is the objective of this assessment?
260)	Favour the choice of existing resources[5] by focussing the production on the specific needs.
[5] We frequently see educational teams rewriting the xth version of an existing aid. However this tropism is often difficult to temper since it expresses the trainers’ fear in the face of exogenous resources and more profoundly a real problem of professional identity in the face of developments difficult to control. This need to produce “one’s own resource” may also express a difficulty of appropriation that is quite justifiable in a complex environment. This aspect takes us back therefore to the question of the professionalization of the parties.
261)	Acquire a skill for assessing a digital training resource both to situate a specific production in relation to what already exists, and to adjust one’s own production to the specifications and/or to adjust one’s aim according to the initial effects obtained with learners.
### Analyse the drawing up process
The assessment processes take place throughout the project and the same is true for the drawing up process. The level of freedom in the choices available decreases with the advance of the project, and the same is also true for the technical aspects. To put it crudely: you cannot wait for the end of a project only to realize that the system you have chosen will not be usable by the population for which it is intended, or that the video digitization technology chosen cannot be deployed in all of the conditions of use of the system.
262)	Each technical choice must be criterion referenced and assessed according to the functionalities sought for in the system implemented.
263)	Check the following criteria:
- stability of the technical system;
- conditions of interoperability;
- conditions of upgradeability;
- facilitator system for basic technical and educational maintenance;
- accessibility for learning activities by the learners.
### Analyse the conducting of the training course
In a quality approach focussed on learner satisfaction, the “conducting” process is the central aspect which needs to be examined in great detail. This process is largely what emerges from the previous processes where the choices made beforehand become visible. It is also the richest process in terms of observations and the possibility of analysing the effects and results.
#### Admission to the training course
264)	Check the presence and relevance of the following points in the information and joining stage:
- the objectives of the training course (subjects, skills or abilities aimed at and levels of expertise aimed at), as well as the ways that these will be verified and validated;
- modularization of the training course (division into units and topics etc.);
- the pedagogical model (transmissive, appropriative, case studies etc.);
- the total length of the training course and the length of each sequence;
- the pedagogical contract;
- the appropriation of the learning environment.
#### Learning support
265)	Check the presence and relevance of the following points in the learning support stage:
- actual functioning of the system (number of appeals to online help, level of user satisfaction); socialization (actual use of collaborative work systems and means of communication made available, level of satisfaction);
- analysis of difficulties linked to inadequate command of ICT (statement of incidents linked to the subject, non-use of all or part of the technological means allowed).
#### Results of learning
Assessment of learning is not specific to e-learning but the software tools available enable very detailed measurements. It is necessary to adjust the level of detail of the information retained to the issues and objectives of the training course. Indeed, having too much information available can easily create confusion and no longer make it possible to distinguish relevant data for the assessment of learning.
Considering the (relative) novelty of the offer of e-learning and its cost, two aspects in particular need to be emphasized.
266)	Take into account the satisfaction rate of the populations concerned.
267)	Take into account the dropout rate observed.
These are probably the indicators that are specific to e-learning insofar as distance may reduce standard links. These indicators should be handled with care depending on the economic model concerned. For example, in one case a low dropout rate may be a positive indicator, but on the other hand in the case of the “annual rate” model, withdrawal improves profitability, initially, if customers accept to pay an initial fixed price.
#### Impact of the training course
To assess the impact of the training course both on the future of the learners and on the development of skills:
268)	Carry out an investigation into the future of the learners after the training course:
- employees undergoing further training at the work station (use of learning), promotion, change of job;
- job seekers.
269)	Assess the institutional impact (structural, organizational, financial and human resources effects):
- transformation of organizations.
- innovation;
- development of skills;
- return on investment;
- expansion of the market, new customers, fame.
270)	Assess the impact in relation to environmental data.
271)	Compare the effects of e-learning with the motivations at the launch of this project:
- significant improvement in access to training in some employment areas;
- improved productivity of training budgets;
- improved treatment of populations, improved rate of access to employment.
Assessment of the impact of training is one of the most sensitive and delicate aspects to successfully conclude. Make sure that you are not “maximalist” and do not expect e-learning to have magical powers which it does not have any more than standard training solutions.
### Analyse costs
This involves understanding the productivity of learning and of its possible increase in connection with the technological change. Three parameters are used to calculate productivity: time, cost and result (which for the training process represents the “value” of the learning).
Two possibilities can be envisaged:
- more is learned within the same time;
- the same amount is learned but in less time (and therefore in both cases proportionally at a lower cost).
The important thing is therefore to increase the results (knowledge or skills acquired) of the learning. If it is true that economic reflection on e-learning, and more widely on training in general, clearly cannot be reduced to the management and calculation of costs, these cannot be avoided and will inevitably be carried out. However, this calculation clearly does not exhaust the question of the relation between the financial resources granted and the many results of the training course, in other words of the productivity or yield of a training system or plan.
It is necessary to prioritize the questions and therefore to make at least one distinction between three problematic layers. They are not naturally unconnected, but they belong to different registers and therefore need to be dealt with using different methods and approaches.
272)	Calculate the production cost of a system and the construction of management monitoring tools. The question needs to be thought out differently depending on the situation: at the project stage, at the time of the design; at the launch; at the stage of the monitoring of the functioning of the system once it has reached "cruising speed".
273)	Compare costs between ordinary training systems and e-learning systems: This involves attempting to compare the costs of a new system in the form of e-learning, to those of a traditional system. If the differential for costs linked to living and travel expenses is relatively easy to calculate, for other expenses we can only compare what is comparable.
274)	Assess the efficiency of a training system: How can you assess the productivity, effectiveness and value added of a system? Training is not only made up of flows of money, but also of other flows that need to be put into the “black box” of learning to ensure that the person is more learned or more competent on finishing the course than (s)he was at the start.
## Improve the system
The introduction of quality control is essential particularly in the field of e-learning since the level of requirements is very high in particular due to the investments that it involves. The study “Quel modèle qualité pour la e-formation?” (“What quality model for e-Training?”)[6] carried out by Préau clarifies this essential aspect quite exhaustively.
[6] Study: “Quel modèle qualité pour la e-formation? Les “normes – qualité” existantes respondent-elles au besoin des acteurs de la e-formation ?” (What quality model for e-Training? Do existing quality standards meet the requirements of participants in e-Training?) © Préau (2002).
The purpose of quality control is to improve results through rationalization of human and material resources and improvement of processes. It is dependent on the objectives defined by the institution in collaboration with its sponsors, but it also raises the question of aims and values. It is a repeated process of improvement that must take into account elements linked to educational effectiveness, but also those linked to satisfaction, costs, the relevance of the technological choices etc.
If the purpose of quality control is to improve the project, it is necessary to make the result of the three preceding subprocesses operational. This therefore involves specifying the nature and form of assessment outputs, its beneficiaries, policy directions and the support plan envisaged.
### Distribute assessment results
Apart from the form used for the distribution of assessment results (reports, indicators, log sheets, syntheses) and the need to back up these assessments with syntheses and recommendations, the essential aspect is still their appropriation by the parties involved.
275)	Assess to improve. The results of the assessment must be widely distributed within a short time span. The transition from the results of the assessment to corrective action must be provided for (work sessions so that the teams concerned draw up a plan of the modifications to be made by order of priority and according to specific time limits).
276)	Include the results of an assessment in professional practice. For training managers, course designers, technicians, trainers or tutors, this is not an easy or insignificant matter since it requires a capacity for occupational reappraisal, being totally available for and listening to the learners.
277)	Include the assessment in e-learning:
- it must be designed, planned and organized beforehand, when designing e-learning;
- it will take place throughout the implementation processes of e-learning (before, during and after);
- the process of distribution, integration of results and deciding on modifications must be provided for and organized;
- it may be drawn up and automated.
The mobilization and involvement of all of the parties are just as important during the stage of assessment and design of corrective action, as they are during the analysis, design, writing up and conducting stages of e-learning.
### Introduce the action plan
To be effective, the assessment process must be anticipated, negotiated, required and shared by all of the participants in the system: the choice of objectives, of the criteria to be accepted, of the subjects to be assessed and of the methods to be used must be known and validated by everyone. Only on this condition will all of the parties concerned be able to accept the approach and to legitimize its results and implications. By entering an assessment process you cannot remain neutral. It is important that it is experienced as a tool for introducing change, encouraging areas of progress both as regards individuals and the management of the organizations.
278)	Introduce corrective action during the implementation of the training course, whether it is not significant in terms of reorganization, or whether it is essential owing to the seriousness of the risk factor. In this case the decision-making process is fast and the general attitude is one of reactivity, similar to that found in all project management.
279)	Act at the end of the project: its purpose is aimed at the renewal, deployment or reform of existing projects but it may also concern the implementation of new projects. In this case it involves the creation of a new project which meets the same requirements for organization and vigilance that we have just described throughout the different stages and processes of this code of practice.
As has been stated throughout this code of practice, this project must follow the same decision, validation and implementation stages even if their introduction will be greatly facilitated by the formalization of the processes that already exist and have been assessed in the previous project.
280)	Appoint a person (the project manager or another person depending on the scale of the system) in order to “support” these controls and to check that they are actually implemented.
281)	Validate, organize and plan the modifications made to the initial system.
282)	Introduce a specific communication system to guarantee that all the participants in the system are informed of the changes made and include them in their professional practice.
# Appendices
## Glossary
Warning	This glossary is a working paper that is liable to change. It does not represent official or definitive definitions

A.I.C.C	Aviation Industry CBT Committee, standard from American civil aviation, aiming to standardize e-learning. (cf. CBT and visit http://www.aicc.org)
Assessment of the training course	The action of assessing, with the help of previously defined criteria, the achievement of the pedagogical and training objectives of a training initiative. / This assessment can be carried out at different times, by different participants (trainee, trainer, client company etc) We may distinguish for example the assessment of satisfaction, assessment of the content of the training initiative, assessment of learning, and assessment of possible transfers to the work situation. / AFNOR X50-750.
Audit of the training course system	Methodical and independent examination applied to a training system, intended to draw up a diagnosis. / It can apply to a training organization, plan or system. The audit of the training system can be used to recommend, in terms of advice, the resources to be implemented by the organization with a view to improvement. / AFNOR X-750.
Blended learning (mixed, hybrid)	Mixed / blended / hybrid training: / A hybrid or mixed system is one that combines varied pedagogical methods. / Literally, blended system implies that the combination of methods is thought out “after” the identification of the elements, in contrast to a hybrid system, which implies blending at the time of conception, ie the introduction of a pedagogical engineering system meeting an identified requirement. / In French, blended is translated by “mixte”. Some texts use the term “mix-formation” (blended training). / Le B.A.BA de la FOAD , FFFOD (ABC of e-learning, FFFOD). / http://www.fffod.org/Upload/Texte/Fichier_9_F.doc
Collaborative learning	Computer Supported Cooperative Learning. / Eg: online collaborative learning sessions between learners for the university degree: “Assistant manager of SME” at the IAE in Caen. / Definitions that already raise a question explored by certain think-tanks in France, which try to make a clear distinction between the field of collaborative learning and the field of cooperative learning. / From this perspective, cooperative work refers to the sharing of tasks between the different participants and pooling, after the event, by juxtaposition of the contributions of each person. Collaborative work on the other hand refers to the joint elaboration of a negotiated and consensus solution. / Collaboration is a method of learning. / It involves a pedagogical technique, the purpose of which is to learn the skills and knowledge of other people and to interact with them. / It also aims to stimulate the development of different viewpoints and to promote interdependence in interactions. / What is the purpose of this method of learning? In addition to the acquisition of training contents (technical and professional contents etc.), collaborative learning can also favour the acquisition of relational skills currently sought by companies. Many of these skills can be grouped together under the generic term “collaboration skills”: / - interpersonal communication; - exchange of information; - negotiation (concerning the aim, the way, the resources etc.); - cooperative or collaborative team work; - functioning by project; - sharing of solutions etc. / These skills represent an additional and complementary acquisition in relation to theoretical, technical or practical contents taught within the framework of the training course, and therefore represent a value added. / Valérie Hellouin “Actualité de la formation permanente” (New issues in continuing education), n° 179, published by Centre INFFO in July/August 2002.
Collaborative work Cf collaborative learning	Between learners, “a group of people interacting in order to set themselves or to accomplish a common target, which involves sharing of tasks and the convergence of the efforts of members of the team”. / Apprendre en collaboration avec d’autres … le travail en équipe (Learning in collaboration with others… teamwork). Théorie et pratiques à l’intention des étudiants et des étudiantes du premier cycle (Theory and practice for first and second year students), ALAOUI, LAFERRIERE, MELOCHE. (1996). Faculty of Science of Laval.
Community of practice	Translation of “communauté de pratique” or “communauté de praticiens” / Informal network of people whose areas of competence are complementary and who are involved in a joint activity. / Synonym: network of exchange of practice - m.n. / NOTE(S): Communities of practice enable those who belong to them to improve their skills by the pooling and sharing of information supplied by members. / Office québécois de la langue française (Quebec Office for the French Language), 2003.
Cooperative work	“Activity of learning in a group, organized in such a way that learning is dependent on the exchange of socially structured information which is carried out between the learners of the group. It is also an activity in which the learner is responsible for his/her own learning and motivated to take part in the learning of others”. / L’apprentissage coopératif (cooperative learning): un défi pour les professeurs de langue (a challenge for language teachers), LOPRIORE, L. (1999). Magazine “Le français dans le monde”. Special issue: apprendre les langues étrangères autrement (a new way of learning foreign languages). / “Allocation of a collective task carried out in a small group, requiring a maximum level of interaction between peers, without the direct and immediate supervision of the trainer”. / Traité des sciences et des techniques de la Formation (Treatise on training science and techniques), CARRE, P. and CASPAR, P. (1999) Dunod, Paris.
Criteria	- Elements that act as support for a judgement; - nature or property of an object (person or thing) according to which an assessment is made of it (Lalande); - collection of scores, measurements, estimates of products that a test must efficiently predict or to which its results must be correlated. / Dictionnaire de l'évaluation et de la recherche en éducation, (Dictionary of Educational Research and Assessment) DE LANDSHEERE, G. (1979) PUF, Paris.
Feasibility study	A study, whose purpose is to determine the conditions for implementing an idea, a product, a technique or a project, to highlight the difficulties that may arise during its implementation and to assess its profitability. / http://www.granddictionnaire.com/
Free or open-source software	Software delivered with its source code so that it can be copied, modified and redistributed, which is thus continually being developed into more advanced versions, in the context of cooperative and community development. / The concept of “free software” originated in the Free Software Foundation (FSF) whose chairman and founder, Richard Stallman, upholds that the use of software for non-commercial purposes should not be subject to restrictions. Although this view is difficult to reconcile with the marketing of software, the underlying idea of cooperative and community development behind the development of free software is, on the other hand, more and more popular. / In spite of certain similarities, we must not confuse free software with freeware, shareware and public domain software. Here, free means “without constraints” and not “free of charge”, even if at present most free software is distributed free of charge or at a very low cost. Free software is also protected by copyright. / The free operating sytem Linux (named after its inventor, the Fin Linus Torvalds, and the Unix system that is at its origin) and the Apache Web server (which got its name from the expression “a patchy server”) are two examples of free software. The term “open-source software” is also used because the source code is made public. / http://www.granddictionnaire.com
Grain	Generic term to refer to the smallest educational unit of an educational course. A granule or grain is a learning object. Microscopic learning objects (basic learning units) are combined to form individual training courses. / http://www.educnet.education.fr/superieur/glossaire.htm
Granularization	Granularizing the training course involves cutting up the content of a subject into numerous items in order to be able to combine them in different educational courses according to the level and expectations of each learner. Granularization enables the creation of courses tailored to individual needs. / http://www.educnet.education.fr/superieur/glossaire.htm
Instruction Design	Collection of coherent methodological approaches that apply to the design of systems of actions and of training systems in order to achieve efficiently the objective set. AFNOR X50-750.
Interactivity	The last example of hyper-modernity? Interactivity is adapted to any purpose: TV and radio programmes must be interactive… Interactivity becomes an inescapable human quality… (at the risk of confusing it with interaction!). It becomes an essential element of user-friendliness at the dawn of the information society. / Educationalists were quick to apply this concept that came from technology and cognitive ergonomics works on man/machine interfaces, and then from software developed during the 1980s. Indeed, the concept of interactivity is able to embody and make operational one of the fundamental principles of "active methods": it is the activity of the learner that makes the term successful. At the meeting place of the convictions of militants of the Freinet method and of zealots of Education by Objectives in its humanist version (cf. Daniel Hameline) or behaviourist version (cf. Mager), everything works towards putting the learner at the centre of the famous educational triangle: learner /trainer /content. This loan from the field of technology must allow the most committed participants to go beyond mere wishful thinking or magic spells… At the start of the 1980s Seymour Papert opened up a real possibility for militants of pedagogical innovation with his prophetic language “Logo”: technology reinforces, transcends and gives life to this learner-centred approach. / http://ressources.algora.org/reperes/comprendre/ticfoad/ticfoad.asp
Interoperability	Ability of heterogeneous information systems to function jointly, thanks to the use of common languages and protocols, and to give reciprocal access to their resources. / N.B.: Interoperability implies that a programme that is part of an open system will also function on another system. One of the basic conditions enabling communication between computers is the use of common languages and protocols. Interoperability needs more than just good technical connectivity, since it requires the use of elements such as standardized programming interfaces and data formats. / http://www.granddictionnaire.com/ / We can also take an interest in the educational dimension of interoperability which takes us back to the questions of granularization and learning objects.
Iterative	Describes a treatment or procedure that carries out a set of operations in a repetitive way until a well-defined condition is satisfied. / Association française de normalisation (French Standardization Association) (1980) Traitement de l'information (Data Processing). Additional experimental vocabulary. Collection Norme expérimentale; Z 61-101 - AFNOR, Paris.
LCMS Cf LMS and Training platform.	Learning Content Management System translated by “Système de gestion de contenu d'apprentissage”. / A LCMS is a system (most often based on Web technologies) that makes it possible to create, validate, publish and manage learning contents. To underdatnd what an LCMS is, it is necessary to start from the following formula: / LCMS = LMS + CMS / (Reminder: / LMS, is considered in many cases as the centre of the e-training system, and its purpose is to simplify the management and organization of training. / CMS (Content Management System) is intended to simplify the creation and management of online content. It enables more frequent updates of resources already published at a lower cost). / http://www.educnet.education.fr/superieur/glossaire.htm
Learning environment	Learning environments: in order to use and then possibly to design interactive educational resources, it is necessary to master the four principles quoted by Depover, Giardina and Marton: /  Communication: one of the basic elements of teaching skills – knowledge of the principles of communication – is essential. It is a question of using this knowledge for the purpose of learning. Whether one chooses Roman Jakobson’s pattern of communication or Lasswell's paradigm (who says what, to whom, by what means, with what effect), it is necessary to master this essential aspect and in particular the various elements of feed back: regulation, correction of the plan etc /  Semiotics: stemming from semiology, this refers to the science and organization of signs that make up messages. This implies reflection on the specificity of textual, sound and visual (static and dynamic)-type signs displayed on a screen in a multimedia environment. /  Learning: it is important both for the trainer-designer and for the trainer-user to identify the type of learning that is the most relevant from the range of theoretical trends (behaviourism, constructivism, cognitivism etc). It is not a question of turning trainers into educational theorists but to ensure the consistency of learning environments according to training populations and objectives. Indeed, these psychopaedagogic considerations have a direct effect on the nature of the guidance to be provided and therefore on the choice of interface to be implemented as regards screen design. /  Systems analysis: an interactive learning environment constitutes a system that links together the different elements involved. This systemic dimension reveals the complexity of these questions. If fact, if one of the elements of the system becomes dysfunctional, the whole system will become ineffective. This is a basic difference from traditional pedagogical methods where the trainer in a real-life situation can make up for a possible technical and/or human fault etc. Systems analysis therefore provides governance and regulation for interactive learning environments. / http://ressources.algora.org/reperes/comprendre/ticfoad/ticfoad.asp.
Learning objects	A learning object is a unit of content that focuses on a specific learning objective. These learning objects may be composed of one or several components or units of information including text, images, videos, sound, animation etc. / Les normes et standards de la formation en ligne : état des lieux et enjeux (Standards of online training: appraisal and issues). Crepuq, September 2002: / http://profetic.org/file/norm-0210-d-RAPPORT.pdf
LMS	Learning Management System: see Training Platform.
LOM	LOM: Learning Object Metadata, metadata (data concerning data that makes it possible to describe information) combined with learning objects. / SC36 – ISO.
Mediatization	Use of a medium that enables communication with learners (this mostly involves electronic documents, multimedia applications transmitted via the Internet and distance learning platforms). / In “Regards croisés sur des pratiques de FOAD” (Reflections on e-learning practice). Collection Champ contre champ. Espace Formateur. (2003) page 124. / http://www.espace-formateurs.org/
Metadata	This is data that defines the content to which it refers. This may be keywords or any other term included in an index area accessible primarily to search engines when they do not carry out a full text search, ie in the main body of the text of the document itself. The codification and classification of the terms used for metadata are essential to ensure that they are used effectively, ie to quickly find the documents sought with the highest relevance and a minimum level of waste and noise (documents not matching the query). / Michel Arnaud, coordinator of the French mirror group AFNOR ISO JTC-SC36.
Netiquette	Set of agreements concerning propriety governing the behaviour of network users, in particular for chat room or email exchanges. / http://www.granddictionnaire.com/
e-learning	Common definition: / e-learning (Open and Distance Learning) is a training system that is not only based on face-to-face learning. / Scholarly definition: (Collectif de Chasseneuil) / E-learning: /  is a system organized, finalized and recognized as such by the participants; /  that takes into account the uniqueness of those concerned in their individual and collective dimension; /  and is based on complementary and plural learning situations in terms of times, places, pedagogical, human and technological mediation and resources. / Le B.A.BA de la FOAD , FFFOD (ABC of e-learning, FFFOD). / http://www.fffod.org/Upload/Texte/Fichier_9_F.doc
Pedagogical contract	The pedagogical contract can be the medium for a personalized training approach. AFNOR X50-751.
Pedagogical resources	In the context of ICT, this refers to digital pedagogical tools that facilitate learning. The terminology that describes these resources is continually changing which does not make them easier to understand! Terms used include: CAI, courseware, tutorials, exercisers, microworld, simulators, training multimedia, digital training tools or products, and multimedia learning environment. / To gain a clearer understanding we need to look on the one hand at the history of the technologies, and on the other hand at the different trends and theories of learning and innovations in pedagogy. / The key concepts of interactivity and hypertext/hypermedia are at the heart of the question and are therefore necessary for a good understanding. / To find out more: / The vocabulary used has changed noticeably over time. Depending on the period, the pedagogical characteristic of the tool has been described: this is the case for CAI for example, even if militants of active methods were disappointed that a debatable teaching model should become a generic term. French Canadians preferred to speak of “pedagogical application of IT” which was more neutral! At other times it was the form that took precedence, for example when the term “training multimedia” was used. / However, the abundance of terms results from a certain confusion in people’s understanding and sometimes from cliquishness: The Ministry of Education felt itself obliged to produce its own acronym by speaking of information and communication technologies for education (technologie de l’information et de la communication pour l’éducation - TICE). More recently, Distance Teaching (enseignement à distance – EAD), Distance Training (formation à distance – FAD), e-learning and then e-training have added to this confusion. / Typology of resources: / Resources based on the behaviourist model: these involve tutorials, exercisers, CAI (computer-aided instruction) which are based on the basic principles of the programmed teaching (breaking down of difficulties, advance from the simple to the more complex, positive reinforcement etc). / Resources based on the constructivist model: these involve microworlds inspired by the work of Seymour Papert and the language LOGO (learning is achieved by giving instructions to the software program and by making mistakes). Flight, train, lorry and car driving simulators are built on this principle. / Resources based on the information theory model: this mainly involves the method used in cases that are based on problem solving processes where the search for information and the formulation of hypotheses make it possible to solve problems inspired by real, but simplified, professional situations. / Structure of the resources: / modularity of the resource: the granularity of the resource corresponds to the size, in terms of the meaning, of the learning sequence. It is currently held that the optimum length of a training grain intended for adults is 30 to 45 minutes. It is not a question of the maximum capacity for concentration, but of the length of a unit which needs to be combined with others. This granularity is important, since it plays an essential role in the notion of the interoperability of resources in heterogeneous systems; /  the level of openness of the resource. / A few references: / La logique de l’honneur, Gestion des entreprises et traditions nationales,(Logic of honour, company management and national traditions) IRIBARNE Philippe, Paris: Seuil, Essais- Points, 1989, 280 p. /  Guide du multimédia en formation, bilan critique et prospectif (Guide to training multimedia, critical report and forecast) Naymark J. (ed.), Paris: Retz, 1999. /  Les environnements d’apprentissage multimédia (multimedia learning environments). Analyse et conception (Analysis and Design) Depover Christian, Giardina Max, Marton Philippe, Paris: L’Harmattan, Paris, p. 177. /  Guide de conception pédagogique et graphique de sites W3 éducatifs (Guide to pedagogical and graphic design of educational websites), APTIC: Denyse GILBERT, University of Laval, Quebec, Canada, / http://aptic.ulaval.ca/guidew3educatif/ / http://ressources.algora.org/reperes/comprendre/ticfoad/ticfoad.asp
Personal training contract	Formalized agreement between a trainer and a learner following from the methods of achieving the pedagogical objectives defined beforehand between the customer and the training contractor.
Personalization of the training course	Among the numerous definitions of personalization, we have adopted the following: A training process is said to be personalized insofar as:  different individuals receive different training services;  these differences result from explicit and methodical decisions. / Formations individualisées (Personalized training courses), Documentation Française, 1995. / To find out more: Two main directions emerge from the approaches of personalized training courses:  one belonging to a mechanistic approach to training: the subject is not automatically consulted to determine training methods and objectives. Although the programme can be adapted by third parties to individual characteristics, the person follows his/her learning without any lucidity, blindly. We shall call this approach “mechanistic personalization”.  and one where the individual really is a participant in his/her learning process. In this case (s)he may define alone or with others the conditions of his/her learning in order to achieve an aim that (s)he has set herself/himself. We will then consider that it is an “autonomizing personalization” approach. / An assessment grid from Quebec known as the grid for assessment of the level of personalization of programmes (Grille d’Évaluation du Niveau d’Individualisation des Programmes - GENIP) sets out to assess the level of personalization of a system on the basis of thirteen parameters: - place; - time; - objectives; - access; - progression; - sequence; - contents; - assessment; - pace; - format (working alone or in a group); - methodes; means of learning; - resource persons, / Personalization is a learning process that offers different learning situations to different people. Learning situations do exist allowing the individual to be master of his/her course, or on the contrary, very preprogrammed situations.
Preventive maintenance	Periodic maintenance of the components of facilities in order to ensure that they function correctly and to detect possible problems before they lead to serious breakdowns. / http://www.granddictionnaire.com/
Project review	In the development life-cycle of a system or software program, systematic examination by specialists of the objectives and requirements of the IT entity. / http://www.granddictionnaire.com/
Proprietary software	Software specific to a given developer, which means that it does not necessarily comply with a standard, that it is not always compatible with other software, that it is protected by copyright and that it is necessary to buy or acquire a licence to be able to use it. / http://www.granddictionnaire.com
Regulation (of learning)	Process linked to assessment, which consists of an adjustment of learning actions and strategies so that the student can progress and achieve the objectives set. / This adjustment can be made by the pupil or by the teacher. / http://www.granddictionnaire.com/
REX	Recovery of experience. Part of quality control. Mainly used in large organizations particularly in the field of security.
SCORM: Sharable Content Object Reference Model	SCORM is not strictly speaking a standard but rather an aggregate standard. It combines the best aspects of the AICC and IMS standards. The ADL (Advanced Distributed Learning http://www.adlnet.org ) SCORM “standard” is now recognized as the definitive standard as regards the design of e-learning and platforms (LMS). / A SCORM course is made up of SCO (Sharable Content Object) objects. An SCO is a unit (or grain) of content that has a pedagogical meaning, that can be reused in another lesson, and which will be recognizable by a SCORM platform. An SCO can be composed of HTML pages, animations, drawings, videos etc. Several SCO can form a Learning Object (LO) and one or several LO can form a lesson. / http://www.definition.be/defipoints/point5.asp
Strategic analysis	Strategic analysis is a rational process, structured to take into account the company in its internal and external environment. / http://www.strategie-pme.com/analyse_strategique.htm. / The field of strategy has been enriched by numerous models, methods and concepts, whose approaches can be structured in 5 main stages: / 1. strategic segmentation (identification within the general activity of the company of relevant groups from the point of view of the formulation of strategy, and therefore of the allocation of resources, from which the strategic study is built); / 2. competitive analysis (analysis of the intrinsic characteristics of fields of activity, determination of the forces that influence them and identification of the motives of the competition); / 3. construction of a lasting competitive advantage; / 4. ways and methods of strategic development (eg: integration, geographic diversification or globalization, linked diversification, diversification etc.); / 5. management of a varied portfolio of activities (use of models of activity portfolios to formalize and facilitate general management). / http://campus.hec.fr/strategor/
Support	What does it concern? / Support functions are tasks, missions and skills that trainers implement in conducting distance learning courses. Functions of direct support of learners, functions of coordination and functions of technical support may be identified. / To find out more / Support is undoubtedly the main function of the trainer, in all systems. Advancing with the learner, accompanying him/her in the construction of knowledge was already the main activity of Socrates, the father of pedagogical maieutics. However, in e-learning, this function takes on a new aspect, so much so that we often speak of new skills. What really changes? / Learning support is not a new function. It does however take on different forms, contingent to the systems implemented. We may distinguish: /  the function of guidance (co-management, with the learner, of the personal training project); /  the function of expertise (guaranteeing the pedagogical aids used and the quality of the knowledge produced by the learner); /  the function of tutorship, either face-to-face or at a distance. / This tutorship can be provided by several people, who share the task: technical tutorship (hot line), didactic tutorship (face-to-face or at a distance), methodological tutorship (face-to-face, e.g. in resource centres, or online). The distance of the learner and his/her isolation increase the need for personalized support, that helps to fight the despondency and demotivation that distance trainees often suffer from. In addition this tutorship must help them to develop aptitudes for autonomous work (organization of documents, working-out and respect for a schedule etc.). Finally, an open or hybrid learning system must re-create the conditions that reintroduce human mediation, including by encouraging work between peers (forum, chat etc.) / The support function of the project is however new and essential in e-learning: all projects of this kind require the function of project manager, who makes the original idea concrete and expresses it in terms of objectives, financing, strategy and setting in motion. Equipped with solid management and communication skills, this project manager, at the head of a project team, is an emerging figure in the field of e-learning, since conducting an e-learning project presents specific features. / Finally, the third facet of the support of e-learning is technical support, which corresponds to new professions (webmaster, computer graphics designer, multimedia assis+B24tant etc.). This support is aimed as much at trainers as at learners: installation and maintenance of the distance learning platform, allocation of user names and passwords to the contributors according to their profiles, technical assistance, help in designing documents and putting them online (elaboration of graphic charters, structuring of documents, mediatization of contents etc.). / http://ressources.algora.org/reperes/comprendre/ticfoad/ticfoad.asp
Traceability	The possibility of keeping a record of certain information, for example in order to be able to assess the quality of a service. Distance learning systems can present a specific advantage in keeping records of all learning and monitoring activities such as training plan negotiations, results of tests, use or resources, treatment of nonconformities etc. / Construire son projet de formation en ligne (Constructing an online training project), BOUTHRY, A. JOURDAIN, C. (2002) Editions d’Organisation, Paris. / "Aptitude à retrouver l'historique, la mise en oeuvre ou l'emplacement de ce qui est examiné" (Ability to find the history, implementation or location of what is being examined). / ISO 9000 definition (version 2000).
Training Platform	Learning Management System: (distance) learning platform / This English term refers to the e-training platform. Computer system designed to optimize, within an Internet or Intranet network, the management of all training activities, including information about the course, registration of the participants, distribution of resources, organization of personalized courses, monitoring by the tutor and tutorship (integrated management of learner-trainer interaction), leadership of learning communities. Depending on their design, they favour entry by content or skills, collaborative or individual work, the acquisition of skills or the organization of knowledge (grains...). / http://www.educnet.education.fr/superieur/glossaire.htm
Training system	Common definition: / “System” refers to any form of training system. / Scholarly definition: / “A formal learning system (term used in Canada to refer to a training system) is a collection of resources. A formal learning system is a collection of material and human resources, corresponding to a specific form of socialization (G. Simmel) intended to facilitate a learning process (Bernard Blandin, 2001). / Le B.A.BA de la FOAD , FFFOD (ABC of e-learning, FFFOL). / http://www.fffod.org/Upload/Texte/Fichier_9_F.doc
XML	Development of SGML language enabling designers of HTML documents to specify their own markers, for the purpose of personalizing the structure of the data that they intend to present. / http://www.granddictionnaire.com

## Working methodology
This code of practice has been drawn up using a standard project management approach:
- formation of a steering committee representative of the diversity of the profession,
- formation of a drafting committee bringing together experts in the field,
- appointment of a project manager,
- elaboration of the conceptual and methodological framework of the project,
- definition of a working schedule including internal and external validation stages.
The elaboration of this code of practice is the result of a rigorous approach:
- call for proposals for hearings,
- hearing of a series of participants involved in E-learning,
- documentary analysis of all French and international literature,
- seminar for the validation and enrichment of an initial series of working papers,
- development hearings concerning areas of tension in the wording,
- final validation procedure of the definitive document.
Drafting of various working papers
- interview grid aimed at project managers,
- interview grid aimed at learners,
- document analysis grid

The present document describes the processes and recommendations to be implemented to develop quality e-learning actions.

Keywords	training, IT application, information exchange, Internet, processes, design, traceability, project management, choice, assessment.

FA136609	ISSN 0335-3931
ICS: 03.100.30 ; 35.240.99